## Slide 1
SAP SUCCESSFACTORS + QUALTRICS EMPLOYEE EXPERIENCE
Scoping workshop and questionnaire
What we need to learn to go live in 3-4 months, with Employee Central and PMGM already live
[Client name] | [Consultant / firm] | 28 October 2026

## Slide 2
We start from a strong base, and a short runway
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
2
2
modules already live
Employee Central and Performance & Goals (PMGM)
3-4
months to go-live
Late January to February 2027
200
questions in 19 sections
84 kick-off questions come first
What this workshop must settle
Scope
Which use cases go live first, for whom, and who owns each
Data
Which Employee Central data and events feed Qualtrics, and how clean they are
Risk
Security, privacy, consultation and module dependencies that could move the date
Notes: Frame the session. Employee Central and PMGM are live, so the people data foundation exists. The tight part is the 3-4 month window with other SuccessFactors modules arriving at the same time.

## Slide 3
Discovery runs in four steps over two weeks
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
3
1
Decide scope
Mark every use case Wave 1, Phase 2 or Out
Day 1-2
2
Kick-off questions
Answer the 84 starred questions with sponsor, HRIS and IT
Week 1
3
Deep dives
Integration and data, privacy and legal, content and 360, comms
Week 1-2
4
Validate plan
Confirm the 16-week plan, risks and Wave 1 scope
Week 2
Questions carry a priority (P1 must answer) and a needed-by week, so the team can answer in the order that unblocks design.
Notes: Questionnaire is completed asynchronously; workshops are used to resolve open decisions rather than read questions aloud.

## Slide 4
Eleven use cases compete for the same window
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
4
Annual Engagement
Fit: High
Pulse & Ad Hoc
Fit: High
Onboarding
Fit: Medium-High
Exit
Fit: Medium-High
Candidate Experience
Fit: Low-Medium
360 / Multi-Rater
Fit: Medium
Manager Effectiveness & Action Planning
Fit: Medium-High
Employee Technology Experience
Fit: Medium
Internal Moves & Return from Leave
Fit: Low-Medium
Well-Being & Inclusion
Fit: Medium
Change & Project Pulses
Fit: High
Fit for a 3-4 month window (hypothesis). Needs EC data only = high; depends on modules not yet live = lower.
Notes: Fit is our hypothesis, not a promise. Ask the sponsor to challenge each rating.

## Slide 5
Starting hypothesis: build the foundation, launch the quick wins
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
5
Wave 1: go-live
Foundation
Integration, directory, hierarchy, roles, anonymity rules
Engagement or Pulse
Needs Employee Central data only
Onboarding and Exit
Triggered by EC hire and termination events
SF adoption pulse
Quick win right after SuccessFactors go-live
Phase 2: follow-on
360 / Multi-rater
Needs competency model and a decision against PMGM
Candidate experience
Depends on Recruiting being live
Technology experience
ITSM integration and owner outside HR
Internal moves, well-being
Proven triggers and legal review first
Notes: This is a hypothesis to challenge. The test is whether each use case needs data or modules that will not exist at go-live.

## Slide 6
Illustrative architecture: Employee Central feeds Qualtrics
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
6
SuccessFactors
Employee Central (live)
PMGM (live)
Hire, transfer, termination events
Org, manager, location data
Integration
Pre-packaged extension
SFTP or API
SAP BTP Integration Suite
Daily or event-driven
Qualtrics Employee Experience
Directory and hierarchy
Engagement, Pulse, Onboarding, Exit, 360
Dashboards, text analytics, action planning
Role-based access by hierarchy
Upcoming SuccessFactors modules
Recruiting, Onboarding, Learning, Succession, Compensation
Add triggers and data when live; interim file or manual feed
Employees, managers, HR
Invitations by email, Teams or SF home
Results and actions back to people
Notes: Illustrative only. Integration options (pre-packaged extension, SFTP, API/Integration Center, SAP BTP Integration Suite) must be validated with SAP and Qualtrics. Section 11 and 12 of the questionnaire cover this.

## Slide 7
Why we are doing this, and how we will know it worked
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
7
CTX
Project Context & Objectives
Why the client is investing, who decides, and what the listening landscape looks like today.
KEY QUESTIONS
Top 3 business outcomes expected from EX
Executive sponsor and decision rights
Current listening tools, results and baselines
Population, countries, languages, worker types
Is the go-live date fixed, and why?
11 questions
8 must answer
11 due by week 4
SUC
Success Measures & Operating Model
KPIs, baselines, business case, run model and the roadmap after go-live.
KEY QUESTIONS
KPIs at 6 and 12 months
Baselines for the chosen KPIs
Business case and benefits owner
Run team and annual survey calendar
Policy on using results in decisions
8 questions
2 must answer
4 due by week 4
Notes: PROJECT CONTEXT & OBJECTIVES
CTX-01 [P1, Week 2] What are the top three business outcomes you expect from Qualtrics EX (for example lower regretted attrition, higher engagement, better onboarding, stronger managers, SuccessFactors adoption)? Please rank them.
CTX-02 [P1, Week 2] Who is the executive sponsor, and what decision rights do they hold over scope, budget and the go-live date?
CTX-03 [P1, Week 2] Which employee listening tools, vendors and programmes run today (engagement, pulse, onboarding, exit, 360)? Please share the last 24 months of results, response rates and survey instruments.
CTX-04 [P1, Week 4] Which existing survey programmes must be replaced, kept, or run in parallel at go-live?
CTX-05 [P1, Week 2] Workforce profile: headcount, countries, legal entities, worker types (employees, contingent, interns), share of shift or deskless staff, and languages spoken.
CTX-06 [P1, Week 2] Is the go-live date fixed? What drives it (contract start, board commitment, business event) and what is the cost of moving it by four weeks?
CTX-07 [P1, Week 2] Which other programmes compete for the same HR, HRIS, IT and communications people over the next four months (other SF module go-lives, payroll cycles, M&A, restructuring)?
CTX-08 [P2, Week 4] Who will own EX after go-live (HR, People Analytics, IT, Internal Comms) and how large is the run team?
CTX-09 [P2, Week 4] Is there an EX framework, employee value proposition or people strategy that survey content and dashboards should align to?
CTX-10 [P2, Week 4] What has worked or failed in past listening efforts (low participation, survey fatigue, no visible action, trust issues)?
CTX-11 [P1, Week 2] Is Qualtrics already used elsewhere in the organisation (CX, brand, research)? If so, share tenant details, data centre and existing administrators.
SUCCESS MEASURES & OPERATING MODEL
SUC-01 [P1, Week 2] Which three to five KPIs define success at 6 and 12 months (participation, eNPS, onboarding satisfaction, regretted attrition, action-plan completion)?
SUC-02 [P2, Week 4] What baselines exist today for those KPIs?
SUC-03 [P1, Week 2] What business case or ROI has been promised internally, and who owns benefits tracking?
SUC-04 [P2, Week 8] What will the operating model look like after go-live: run-team size, skills, annual programme calendar, centre of excellence?
SUC-05 [P2, Post go-live] How will content and adoption be reviewed quarterly, and who approves new use cases?
SUC-06 [P3, Post go-live] What scale-up is expected in 12-24 months (countries, subsidiaries, populations)?
SUC-07 [P3, Post go-live] What executive reporting cadence on EX outcomes is expected?
SUC-08 [P2, Week 4] What policy governs use of results in performance, promotion or pay decisions?

## Slide 8
Scope, cadence and contract: the decisions that shape everything
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
8
USE
Use-Case Selection & Prioritisation
Which Employee Experience use cases go live first, for whom, how often, and who owns each.
KEY QUESTIONS
Mark each use case Wave 1 / Phase 2 / Out
Minimum viable launch if time is tight
Use cases blocked by modules not yet live
Cadence and blackout periods
9 questions
6 must answer
8 due by week 4
COM
Licensing, Commercials & Contracting
Contract route, licensed products, tenant, data centre and procurement readiness.
KEY QUESTIONS
Contract route and licensed products
Tenant provisioned? Which data centre?
AI features licensed and permitted
Implementation partner and SAP/Qualtrics contacts
Procurement and vendor risk review status
8 questions
5 must answer
8 due by week 4
Notes: USE-CASE SELECTION & PRIORITISATION
USE-01 [P1, Week 2] For each use case on the Use Case Map tab, mark Wave 1 (go-live), Phase 2, or Out of scope.
USE-02 [P1, Week 2] For each in-scope use case, who is the business owner, who is the audience, and what decision will the data drive?
USE-03 [P1, Week 2] If only one or two use cases could be live in 3-4 months, which would they be and why?
USE-04 [P1, Week 4] Which use cases depend on SuccessFactors modules that are not yet live, and could they start with a file-based or manual trigger?
USE-05 [P2, Week 4] Beyond the standard list, are there other use cases (M&A integration, return-to-office, restructuring, safety culture, well-being, inclusion, SuccessFactors adoption)?
USE-06 [P1, Week 4] Which populations are in scope for each use case (all employees, countries, entities, job families, new joiners, leavers, contingent workers)?
USE-07 [P1, Week 4] How often must each use case run (annual, quarterly, event-triggered, always-on), and what are the blackout periods (year-end, payroll, appraisal cycles, local holidays)?
USE-08 [P2, Week 8] Will one listening calendar govern engagement, pulse and lifecycle surveys, and who owns it?
USE-09 [P2, Week 4] Which surveys should be tied to the SF PMGM cycle (for example 360 feedback inside the performance cycle, or a post-review pulse)?
LICENSING, COMMERCIALS & CONTRACTING
COM-01 [P1, Week 2] How is Qualtrics EX contracted: SAP Endorsed Apps agreement, directly with Qualtrics, or via a reseller? Which products or SKUs (Engagement, Pulse, Onboarding, Exit, 360, Lifecycle, Employee Technology Experience)?
COM-02 [P1, Week 2] What are the licensed participant counts per product, and the contract start date and term? Does the licence start before the build begins?
COM-03 [P1, Week 2] Is the Qualtrics tenant (brand) already provisioned, and in which data centre region?
COM-04 [P2, Week 4] Are AI features (Qualtrics Assist, text analytics, conversational feedback) licensed, and permitted under your internal AI policy?
COM-05 [P2, Week 4] What budget is approved for implementation, change management, translation and run costs (admin effort, partner support)?
COM-06 [P1, Week 2] Who is the implementation partner, and which SAP and Qualtrics contacts (account executives, solution architects) are engaged?
COM-07 [P1, Week 2] What is the status of procurement, vendor risk assessment and data processing agreements for Qualtrics, and how long do these normally take?
COM-08 [P2, Week 4] Are there other costs to plan for: integration middleware (SAP BTP / Integration Suite), SSO, premium support, benchmarks?

## Slide 9
Engagement and pulse: the foundation programmes
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
9
ENG
Employee Engagement Survey
Annual or biannual census engagement programme, models, anonymity, reporting cuts and benchmarks.
KEY QUESTIONS
Existing model and trend continuity
Reporting cuts and minimum group size
Anonymous vs confidential
Handling sensitive open-text comments
Manager action plans after results
11 questions
7 must answer
5 due by week 4
PLS
Pulse & Ad Hoc Listening
Always-on, quarterly, topic-based and event-driven pulses, governance and fatigue control.
KEY QUESTIONS
Which pulse programmes are needed
Who can launch a pulse, and fatigue limits
Delivery channels needed
Real-time alerts and case routing
8 questions
3 must answer
3 due by week 4
Notes: EMPLOYEE ENGAGEMENT SURVEY
ENG-01 [P1, Week 4] Is there an existing engagement model or index (composite index, eNPS, drivers)? Must trend continuity with historical results be preserved?
ENG-02 [P1, Week 4] Will you use the Qualtrics best-practice engagement library, a custom model, or a hybrid? Who approves final content?
ENG-03 [P2, Week 4] Census or sample? What participation target do you set, and what was achieved last time?
ENG-04 [P1, Week 4] Which results cuts are required (org unit, location, job level, tenure, age band, gender, manager)? What is the minimum group size for reporting?
ENG-05 [P1, Week 4] Will the survey be anonymous or confidential? Will SF attributes be attached to responses, and how will employees be told?
ENG-06 [P2, Week 8] Is benchmarking required (internal, industry, external)? Against which peer groups?
ENG-07 [P1, Week 8] Who sees results (executives, HRBPs, all people managers), and when? What is the cascade process?
ENG-08 [P1, Week 8] How will open-text comments be handled: languages, redaction of names, and escalation of sensitive content (harassment, safety)?
ENG-09 [P1, Week 8] What are managers expected to do with results (action plans, deadlines, tracking)? Should plans link to SF goals or development plans?
ENG-10 [P2, Week 8] What survey window and reminder pattern are planned, and how will frontline or deskless staff take part (mobile, kiosk, QR code, personal links)?
ENG-11 [P2, Post go-live] Do you expect to link engagement to attrition, performance (PMGM ratings) or other HR outcomes, and is that permitted by policy and employee representatives?
PULSE & AD HOC LISTENING
PLS-01 [P1, Week 4] Which pulse programmes do you need (always-on, quarterly, topic-based, post-event, manager pulse)?
PLS-02 [P1, Week 4] Who may launch a pulse (central HR only, or delegated to HRBPs and managers)? What caps prevent fatigue (maximum surveys per employee per quarter)?
PLS-03 [P2, Week 8] How will respondents be sampled (full population, random sample, rotating cohorts)?
PLS-04 [P2, Week 8] Who curates the standard pulse question bank, and what is the target length (items and minutes)?
PLS-05 [P1, Week 4] Which delivery channels are needed: email, SF home page or Engagement card, MS Teams, Slack, SMS, mobile, QR codes?
PLS-06 [P2, Week 8] For ad hoc, event-driven pulses (restructuring, policy change, SuccessFactors go-live), what approval workflow and turnaround time are expected?
PLS-07 [P2, Post go-live] Should low scores trigger real-time alerts or cases to HRBPs or managers? Which case or ticketing system would receive them?
PLS-08 [P2, Week 8] Who sees pulse results, at what minimum group size, and how quickly after close?

## Slide 10
Lifecycle surveys depend on events and on modules still to come
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
10
LCE
Lifecycle Moments: Onboarding, Exit & Candidate
Event-triggered surveys driven by Employee Central events (hire, transfer, leave, termination).
KEY QUESTIONS
Which lifecycle moments are in scope
EC trigger and event reasons per moment
Onboarding cadence and hiring volumes
Exit survey timing and exclusions
Escalation protocol for serious issues
14 questions
8 must answer
9 due by week 4
UPC
Upcoming SuccessFactors Modules & Sequencing
How other modules going live in the same window affect triggers, data, testing and calendars.
KEY QUESTIONS
SF module go-live dates in the window
EX needs fed into other module designs
Planned EC changes that affect the feed
PMGM cycle calendar and collisions
10 questions
6 must answer
7 due by week 4
Notes: LIFECYCLE MOMENTS: ONBOARDING, EXIT & CANDIDATE
LCE-01 [P1, Week 2] Which lifecycle moments are in scope: candidate, pre-boarding, Day 1 / 30 / 90 / 180, probation end, promotion, transfer, return from leave, manager change, exit (voluntary or involuntary), alumni?
LCE-02 [P1, Week 2] For each moment, what is the EC trigger (hire date, position start, event reason, employment status, termination date)? Which event reasons apply?
LCE-03 [P1, Week 2] Is SAP SuccessFactors Onboarding (or another tool) live at go-live? If not, what is the system of record for new-hire tasks and data?
LCE-04 [P1, Week 4] What are the monthly hiring volumes by country, and what survey cadence is wanted (days since hire) for new hire, manager and buddy?
LCE-05 [P1, Week 4] How should exit surveys work: which exit types are included (resignation, retirement, dismissal, contract end), and should they be sent before or after the last day?
LCE-06 [P1, Week 4] After offboarding, how will leavers be reached (personal email) and what are the policy and legal limits on holding that data and on alumni contact?
LCE-07 [P2, Week 8] Will a self-service survey complement or replace HR-led exit interviews? Is manager input about the leaver required?
LCE-08 [P2, Week 8] Is Recruiting Management in scope and live? At which stages should candidate surveys trigger (applied, interviewed, offered, declined, hired), and what applicant-privacy limits apply?
LCE-09 [P3, Post go-live] Are surveys needed for internal moves, promotions, return from leave or manager change?
LCE-10 [P1, Week 4] When a new hire or leaver raises a serious issue (harassment, safety, discrimination), who is notified, how fast, and what happens to anonymity?
LCE-11 [P2, Week 8] Do managers see onboarding and exit results for their teams, and under what anonymity rules?
LCE-12 [P1, Week 2] How reliable are hire and termination dates, business email and manager assignment in EC today? Are back-dated, future-dated or mass-uploaded records common?
LCE-13 [P2, Week 8] What annual volumes do you expect for each lifecycle type?
LCE-14 [P2, Week 4] Which countries have specific rules for onboarding or exit surveys (consultation, consent, restricted data)?
UPCOMING SUCCESSFACTORS MODULES & SEQUENCING
UPC-01 [P1, Week 2] Which SuccessFactors modules go live in the next 3-4 months (for example Recruiting, Onboarding, Learning, Succession & Development, Compensation, Time, Payroll) and what are their dates? Please complete the SF Module Readiness tab.
UPC-02 [P1, Week 4] For each module, does an EX use case need its data (onboarding task completion, course completion, requisition stages)? Is a manual or file-based interim acceptable?
UPC-03 [P1, Week 2] Can EX requirements be fed into the design workshops of those other modules now (fields, event reasons, status codes)?
UPC-04 [P1, Week 2] Which EC configuration changes are planned (new fields, org restructure, position management, event reasons) that would affect the EX data feed?
UPC-05 [P2, Week 8] How will SuccessFactors half-yearly releases be handled, and what test windows apply?
UPC-06 [P2, Week 4] Is the same partner implementing the other modules and Qualtrics? Where does resource overlap?
UPC-07 [P1, Week 4] When do other modules cut over and hold hypercare, and how does that collide with EX testing and pilot?
UPC-08 [P3, Post go-live] Is Workforce Analytics or SAC planned and should it consume EX data?
UPC-09 [P1, Week 2] What is the PMGM cycle calendar (goals, reviews, calibration)? Which PMGM data (ratings, goals) may be used with survey data?
UPC-10 [P2, Week 8] Are further EC rollout waves planned (new countries or entities) that will expand the EX population?

## Slide 11
360 feedback and managers: from insight to action
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
11
360
360 / Multi-Rater Feedback
Subjects, evaluators, workflow, competencies, reports and the Qualtrics 360 vs PMGM decision.
KEY QUESTIONS
Purpose of 360: development vs evaluation
Qualtrics 360 vs PMGM multi-rater
Rater workflow: predefined, nominated or open
Competency model, rating scale and languages
14 questions
8 must answer
8 due by week 4
MGR
Manager Effectiveness & Action Planning
Manager dashboards, expectations after results, and closing the loop with action plans.
KEY QUESTIONS
Manager action-plan expectations
How a manager is defined; small teams
Follow-up for low-scoring teams
Manager access: dashboard vs PDF
9 questions
3 must answer
4 due by week 4
Notes: 360 / MULTI-RATER FEEDBACK
360-01 [P1, Week 2] Is 360 in scope for go-live? What is its purpose: development only, leadership assessment, talent-review input, or performance input?
360-02 [P1, Week 2] SF PMGM is already live. Does it already run multi-rater or 360 feedback? Which tool will be the system of record for 360 (Qualtrics 360 or PMGM), and what drives the choice?
360-03 [P1, Week 4] Who are the subjects (all managers, senior leaders, high potentials)? How many, and how often (annual, cycle-aligned)?
360-04 [P1, Week 4] Which workflow model applies: predefined subject-evaluator pairs, subject nominates from a predefined list, or open nomination? Is manager approval of raters required?
360-05 [P1, Week 4] Which rater categories (manager, peers, direct reports, skip-level, customers, external) and what minimum raters per category before results show?
360-06 [P2, Week 8] Should the project run in waves (nominations, evaluations, report release), and how long should each wave last?
360-07 [P1, Week 4] Is there a leadership competency model? How many competencies and items, which rating scale, which open-ended questions, which scoring categories, and which translations?
360-08 [P1, Week 4] How will subject and evaluator data be derived from EC: reporting lines, dotted-line or matrix managers, project teams?
360-09 [P2, Week 8] What should subject reports contain, and who sees them (subject, manager, HRBP, coach)? Are norm groups or benchmarks needed?
360-10 [P2, Week 8] How do 360 results flow to development plans (SF Succession & Development, Learning) or stay outside SF?
360-11 [P2, Week 8] Who writes invitation and reminder messages, in which languages, and who coaches subjects on results?
360-12 [P2, Week 8] Are external evaluators (customers, vendors) or contingent workers included, and how is their data handled?
360-13 [P1, Week 4] May 360 results be used in talent, promotion or pay decisions? What do the legal team and employee representatives say?
360-14 [P2, Week 8] Which subjects will pilot, and when? What success criteria would let you scale?
MANAGER EFFECTIVENESS & ACTION PLANNING
MGR-01 [P2, Week 4] Is manager effectiveness a named use case (upward feedback, manager pulse, manager scorecard)?
MGR-02 [P1, Week 4] What must managers do after results arrive: required action plans, deadlines, tracking and nudges?
MGR-03 [P2, Week 8] Do you have manager development content (internal or from Qualtrics) to recommend alongside results? Should it link to SF Learning?
MGR-04 [P1, Week 4] How is a manager defined for reporting (direct reports, full hierarchy roll-up, matrix)? What happens when a manager has fewer reports than the minimum group size?
MGR-05 [P2, Week 8] What follow-up applies to low-scoring teams (HRBP involvement, targeted support)?
MGR-06 [P2, Post go-live] Who tracks action-plan completion, and how is it reported to executives?
MGR-07 [P2, Post go-live] Should action plans link to SF goals, PMGM or development plans?
MGR-08 [P1, Week 4] How many managers need access, and will they use dashboards (SSO) or receive PDFs or emails?
MGR-09 [P2, Week 8] Who will train managers to read results and run team discussions? Are conversation guides needed?

## Slide 12
Technology experience, content, scales and languages
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
12
ETX
Employee Technology Experience
Measuring the experience of tools and services, including SuccessFactors adoption itself.
KEY QUESTIONS
Is technology experience in scope?
Owner outside HR for technology experience
ITSM tool and ticket creation
Measure SuccessFactors experience itself
7 questions
1 must answer
3 due by week 4
SUR
Survey Content, Scales & Languages
Question libraries, rating scales, translations, branding, accessibility and consent text.
KEY QUESTIONS
Languages and translation process
Rating scales to standardise
Mandatory consent and privacy text
Qualtrics library vs custom content
10 questions
5 must answer
6 due by week 4
Notes: EMPLOYEE TECHNOLOGY EXPERIENCE
ETX-01 [P2, Week 4] Is Employee Technology Experience in scope? Which tools and services (laptops, VPN, collaboration, service desk, SuccessFactors itself)?
ETX-02 [P2, Week 4] Who owns it (CIO, service desk, digital workplace) and is there sponsor and budget?
ETX-03 [P2, Week 8] Which ITSM or ticketing tool is in use (ServiceNow, Jira, other)? Should low scores create tickets?
ETX-04 [P2, Week 8] What triggers these surveys: ticket closure, device refresh, a new SF release, or a periodic cycle?
ETX-05 [P1, Week 4] Do you want to measure employee and manager experience of SuccessFactors itself (EC self-service, PMGM, new modules) right after go-live?
ETX-06 [P3, Post go-live] Is device, location or application data beyond EC needed for segmentation?
ETX-07 [P3, Post go-live] Which technology KPIs are targeted (satisfaction, effort, time-to-resolve)?
SURVEY CONTENT, SCALES & LANGUAGES
SUR-01 [P1, Week 4] Which languages are required per use case? What is the source language, translation method (human, machine plus review) and who validates?
SUR-02 [P1, Week 4] Which rating scales and wording standards must be used (5, 7 or 10 point, agree/disagree, eNPS) to stay comparable with history?
SUR-03 [P1, Week 4] Which demographic attributes come from SF (hidden metadata) and which are asked? Are any categories restricted in certain countries (gender, ethnicity, age, disability)?
SUR-04 [P1, Week 4] What privacy notice, consent text and mandatory statements must appear on each survey?
SUR-05 [P2, Week 8] What branding is required (logo, colours, tone) and which accessibility standard (for example WCAG) must surveys meet?
SUR-06 [P2, Week 8] What accessibility needs exist (screen readers, low bandwidth, shift workers, kiosks)?
SUR-07 [P2, Week 4] What survey length targets apply, and who signs off on content?
SUR-08 [P1, Week 4] Will you use Qualtrics best-practice libraries (engagement, onboarding, exit, 360, well-being, candidate) as the baseline, and how much customisation is allowed?
SUR-09 [P3, Week 8] Which scoring conventions apply (favourable %, mean, top-box)?
SUR-10 [P3, Week 8] Would you accept AI-assisted follow-up questions on vague comments (conversational feedback)?

## Slide 13
Integration and data decide the schedule
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
13
INT
SuccessFactors Integration & Architecture
How Employee Central data and events reach Qualtrics, authentication, environments and monitoring.
KEY QUESTIONS
SF instances, data centre and identity provider
Preferred integration method for employee data
Sync frequency and real-time needs
Embed surveys inside SF home or mobile
Architecture approvals and change freezes
15 questions
10 must answer
10 due by week 4
DAT
Employee Data, Hierarchy & Attributes
Which Employee Central fields drive reporting hierarchies, segmentation, triggers and eligibility.
KEY QUESTIONS
EC fields needed in Qualtrics
EC data quality: manager, email, location
Hierarchy that drives reporting
Who is eligible to be surveyed
13 questions
10 must answer
11 due by week 4
Notes: SUCCESSFACTORS INTEGRATION & ARCHITECTURE
INT-01 [P1, Week 2] Describe the SuccessFactors landscape: instances (test, preview, production), data centre, EC release status, identity provider and SSO.
INT-02 [P1, Week 2] What is the preferred method for sending EC employee data to Qualtrics: pre-packaged SF extension, SFTP file, API or Integration Center, or SAP BTP Integration Suite? Any constraints?
INT-03 [P1, Week 2] Do you have SAP BTP / Integration Suite today? Who has the skills and capacity to build and run the integration?
INT-04 [P1, Week 4] How often must data sync (daily full, daily delta, near real time)? Which fields need near-real-time updates (hire for onboarding, termination for exit)?
INT-05 [P1, Week 4] How will EC events (hire, transfer, termination) trigger surveys: SF Intelligent Services events, Integration Center, or scheduled delta files? Is Intelligent Services enabled?
INT-06 [P2, Week 8] Do surveys need to appear inside SF (home page tile, Engagement card, mobile app)? On which SF home page version?
INT-07 [P2, Post go-live] Should results or action plans flow back to SF (development plans, goals, talent profile) or to a data warehouse (SAC, Datasphere, BW)?
INT-08 [P1, Week 2] Which identity standard will be used for employee access (SAML or OIDC, which IdP)? What is the fallback for employees without SSO?
INT-09 [P1, Week 4] How many Qualtrics sandbox and production environments are needed, how often is SF preview refreshed, and what is the policy on test data (anonymised or real)?
INT-10 [P1, Week 4] What API user, OAuth, IP allow-list and permission roles will the integration need, and who approves them?
INT-11 [P2, Week 8] Who monitors failed syncs, how will alerts be raised, and what SLA is expected?
INT-12 [P1, Week 2] What architecture-board approvals and change-freeze windows apply in the next four months?
INT-13 [P2, Week 8] Is data needed from outside EC (Employee Central Payroll, time tracking, ITSM, other HR systems)?
INT-14 [P1, Week 4] Do firewalls or mail filters need allow-listing for Qualtrics survey links? How is email deliverability handled (sender domain, SPF, DKIM)?
INT-15 [P3, Post go-live] Do People Analytics or Workforce Analytics pipelines need to consume EX data?
EMPLOYEE DATA, HIERARCHY & ATTRIBUTES
DAT-01 [P1, Week 2] Which EC fields are needed in Qualtrics (person, employment, job, organisation: legal entity, business unit, division, department, location, cost centre, job family, level, manager, position)? Please complete the Data Inventory tab.
DAT-02 [P1, Week 2] How complete and trusted is EC data (manager, email, location, job level)? Which known gaps exist?
DAT-03 [P1, Week 2] Which organisational structure drives reporting (reporting line or organisation units)? How many levels and units exist?
DAT-04 [P1, Week 4] How are matrix, dotted-line, concurrent employment, global assignments and secondments handled? Which manager and organisation does each person report under?
DAT-05 [P1, Week 4] Which demographic attributes exist in EC and are approved for survey analysis (gender, age band, tenure, nationality, and so on)?
DAT-06 [P1, Week 4] Who is eligible to be surveyed: active, on leave, notice period, contingent, part-time, future hires? What are the exclusion rules?
DAT-07 [P1, Week 4] What contact data is available: business email coverage, personal email, mobile number for deskless staff, preferred language?
DAT-08 [P2, Week 8] Where should derived attributes (tenure band, age band, span of control) be calculated: EC, middleware or Qualtrics?
DAT-09 [P2, Week 8] Is there historical survey data or historical organisation snapshots to load for trend reporting? Format, volume and quality?
DAT-10 [P1, Week 4] What retention periods apply per use case? How are leavers' data deletion and erasure requests handled?
DAT-11 [P1, Week 2] Are reorganisations planned between now and go-live, and how will hierarchy changes during a survey window be handled (snapshot or live)?
DAT-12 [P1, Week 2] Which unique identifier will be the key between EC and Qualtrics (person ID, user ID), and how will pseudonymisation be handled?
DAT-13 [P2, Week 4] Are there entities or populations not on EC (acquisitions, joint ventures, contractors)? Should they be included and from which source?

## Slide 14
Reporting, AI and who gets to see what
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
14
RPT
Reporting, Dashboards & Analytics (incl. AI)
Audiences, dashboards, distribution, text analytics, and joining survey data with SF outcomes.
KEY QUESTIONS
Reporting audiences and needs
AI text analytics and summary approval
Joining survey data with SF outcomes
Agreed definitions for custom metrics
11 questions
3 must answer
4 due by week 4
ROL
Roles, Access & Governance
Administrator model, role design by hierarchy, approvals, segregation of duties and support.
KEY QUESTIONS
Brand admins vs project admins
Viewer roles mapped to hierarchy
Who creates, approves and releases surveys
EX steering and governance body
8 questions
5 must answer
5 due by week 4
Notes: REPORTING, DASHBOARDS & ANALYTICS (INCL. AI)
RPT-01 [P1, Week 4] Which reporting audiences exist (executives, HRBPs, managers, employees, People Analytics) and what does each need to see?
RPT-02 [P2, Week 8] Which dashboard types are must-have: executive overview, manager dashboard, heat map, driver analysis, comparison, trend?
RPT-03 [P2, Week 8] How will reports be distributed: dashboard login, scheduled email, PDF, embedded in SF?
RPT-04 [P2, Week 8] Who needs live response-rate tracking and at what granularity (without identifying respondents)?
RPT-05 [P1, Week 4] Which text analytics and AI summaries (Qualtrics Assist) are in scope, in which languages, and do Legal and employee representatives approve them?
RPT-06 [P1, Week 4] Will survey data be combined with SF data (turnover, PMGM performance rating, promotion, tenure) for analysis? What safeguards apply?
RPT-07 [P2, Week 8] Which internal targets and external benchmarks apply?
RPT-08 [P2, Week 8] Do reports need local-language labels or corporate templates?
RPT-09 [P2, Post go-live] Will raw data go to a data warehouse or People Analytics, how often, and who holds access?
RPT-10 [P2, Week 8] What accessibility and mobile support is needed for dashboards?
RPT-11 [P2, Week 4] Which custom metrics (eNPS, engagement index composition, attrition-risk index) need agreed definitions and owners?
ROLES, ACCESS & GOVERNANCE
ROL-01 [P1, Week 2] Who will be Brand Administrators and who will be EX project administrators? Brand Administrators have full platform access including the directory; Employee Insights Administrators can build projects but cannot access the directory or admin page.
ROL-02 [P1, Week 4] Define viewer roles (executives, HRBPs, managers, regional HR, employee representatives) and map each to hierarchy-based access.
ROL-03 [P1, Week 4] Who can create and launch surveys, approve content and release results? What approval chain and SLA apply?
ROL-04 [P1, Week 4] Who may see raw comments or respondent-level data? What segregation of duties applies between administrators, HRBPs and IT?
ROL-05 [P2, Week 8] Will joiner-mover-leaver access be automated from SF roles or managed manually?
ROL-06 [P1, Week 2] Which governance body oversees EX (steering committee, content council, privacy officer)? How often does it meet?
ROL-07 [P2, Week 8] What support model is expected (employee help, administrators, vendor) and in which languages and hours?
ROL-08 [P2, Post go-live] How will changes to surveys and participant data after launch be documented and audited?

## Slide 15
Privacy, consultation and trust come before launch
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
15
SEC
Security, Privacy & Compliance
Residency, anonymity, consultation, consent, retention, AI governance and vendor security review.
KEY QUESTIONS
Data residency and cross-border transfer
Works council and union consultation timelines
Anonymity thresholds and exceptions
Vendor security review status
12 questions
10 must answer
10 due by week 4
CMM
Communications, Change & Adoption
Invitations, sender, trust messaging, manager toolkits, training and closing the loop.
KEY QUESTIONS
Sender, domain and channels for invitations
Internal Comms engaged; channels available
You said, we did: closing-the-loop plan
Clashing campaigns and SF go-live comms
10 questions
5 must answer
5 due by week 4
Notes: SECURITY, PRIVACY & COMPLIANCE
SEC-01 [P1, Week 2] Where must employee data be stored and processed? Are there restrictions on cross-border transfer (EU, India, China, Middle East, other)?
SEC-02 [P1, Week 2] Has a DPIA or privacy impact assessment been done or required? Who is the DPO and when must they be consulted?
SEC-03 [P1, Week 2] Which countries require works council, union or employee representative consultation, and what are the lead times?
SEC-04 [P1, Week 4] What anonymity commitments apply: minimum group size, suppression of small groups, comment redaction, and who approves exceptions?
SEC-05 [P1, Week 4] What is the legal basis (legitimate interest or consent) and the required privacy notice wording for each country?
SEC-06 [P1, Week 4] Which EC attributes are classified sensitive or restricted? Are any prohibited from leaving EC?
SEC-07 [P1, Week 4] What SSO, MFA, session, admin-access and IP-restriction policies apply?
SEC-08 [P1, Week 2] What security evidence is required from the vendor (certifications, pen-test reports, sub-processor list)? Where does the review stand?
SEC-09 [P2, Week 8] How are data subject access requests involving survey data handled?
SEC-10 [P1, Week 4] What is your protocol for sensitive disclosures in comments (harassment, safety, wellbeing risk): duty of care, escalation path, limits of anonymity?
SEC-11 [P2, Week 8] What audit logging is required (who accessed which results) and how will logs be exported?
SEC-12 [P1, Week 4] Has Legal assessed AI-based analysis of employee data (sentiment, attrition prediction) under internal AI policy and applicable regulation, including EU AI Act treatment of employment-related AI?
COMMUNICATIONS, CHANGE & ADOPTION
CMM-01 [P1, Week 4] Who sends invitations (executive, HR, manager), from which sender name and email domain, over which channels?
CMM-02 [P1, Week 4] Is Internal Communications engaged, and which channels exist (intranet, Teams, town halls, posters for frontline staff)?
CMM-03 [P1, Week 4] What employee-facing FAQ and privacy message will explain what happens to results?
CMM-04 [P2, Week 8] What reminder cadence and tone are planned, and will managers receive response-rate nudges?
CMM-05 [P2, Week 8] What toolkit will managers receive to explain the survey and discuss results?
CMM-06 [P1, Week 8] How and when will you communicate what changed as a result (you said, we did), and who owns it?
CMM-07 [P2, Week 4] What changes for HR, managers and employees, who might resist, and what training is needed?
CMM-08 [P2, Week 8] What training is planned for administrators, HRBPs and managers (formats, lead times)?
CMM-09 [P1, Week 4] Which other surveys, campaigns or SuccessFactors go-live communications run in the same period, and how will they be coordinated?
CMM-10 [P2, Week 8] What local-language adaptation is needed for communications by country?

## Slide 16
Ten decisions we need in the first two weeks
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
16
1
Executive sponsor and decision rights
2
Is the go-live date fixed, and why?
3
Mark each use case Wave 1 / Phase 2 / Out
4
Minimum viable launch if time is tight
5
Contract route and licensed products
6
Preferred integration method for employee data
7
Which lifecycle moments are in scope
8
Qualtrics 360 vs PMGM multi-rater
9
Works council and union consultation timelines
10
SF module go-live dates in the window
Notes: Each decision links to a question ID in the questionnaire.

## Slide 17
Illustrative 16-week plan: go-live in weeks 14-15
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
17
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
2 Nov
30 Nov
28 Dec
25 Jan
15 Feb
Mobilise & discover
Design
Build & integrate
Test & pilot
Go-live preparation
Go-live
Hypercare & handover
Shaded weeks 8-9: year-end holidays, expect lower capacity
Security, privacy and consultation work starts in week 1 because it often gates access to real employee data.
Notes: Start Monday 2 November 2026. W14 starts 1 February 2027. Year-end holidays typically remove one to two weeks of capacity; adjust to regional calendars.

## Slide 18
Six risks most likely to move the date
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
18
20
Vendor security, privacy or DPIA review runs past the build start
Start reviews in week 1; share Qualtrics security pack early; build on test data in the meantime
16
Other SF modules go live in the same window and consume the same people
Agree a single resource plan and change calendar; avoid EX testing during cutovers
16
EC data quality (manager, email, location) creates wrong survey populations
Run a data-quality profile in weeks 2-3; fix at source; add exception reports
15
Works council or union consultation required in one or more countries
Identify countries in week 2; launch in unaffected countries first; prepare consultation pack
12
Integration capacity (BTP or API skills) is not available
Confirm the build owner in week 2; fall back to SFTP file feed for Wave 1
12
Lifecycle triggers depend on modules that are not yet live
Use EC hire and termination events; manual or file triggers for the rest; defer candidate use case
Notes: Starting estimates; replace with the client's view. Full register in the workbook.

## Slide 19
What we need from you next
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
19
This week
Confirm executive sponsor and decision rights
Share past survey results and reports
Start vendor security and privacy review
Name the project team
By end of week 2
Mark every use case Wave 1, Phase 2 or Out
Complete SF Module Readiness tab
Confirm integration method and owner
Identify countries needing consultation
By end of week 4
Complete the Data Inventory
Freeze survey content and languages
Agree anonymity thresholds and roles
Sign off Wave 1 scope and plan
Companion files: Excel workbook (live tracker), Word document (client-facing), Markdown (for editing and version control).
Notes: Close with named owners and dates.

## Slide 20
Sources and caveats
Qualtrics EX scoping | SAP SuccessFactors | [Client name]
20
Qualtrics Support: Step 1, Getting Ready to Launch Your 360 Project: https://www.qualtrics.com/support/employee-experience/getting-started-employee-experience/360-onboarding/form-building/
Qualtrics and SAP announce new partnership (SAP Endorsed Apps), Jan 2025: https://www.qualtrics.com/articles/news/qualtrics-and-sap-announce-new-partnership-to-help-organizations-deliver-great-employee-experiences/
SAP Store: Qualtrics XM for Employee Experience: https://www.sap.com/uk/products/hcm/partners/qualtrics-llc-qualtrics-employee-experience.html
SAP User Groups: Qualtrics / SuccessFactors integration roadmap (archived deck): https://assets.dm.ux.sap.com/webinars/sap-user-groups-k4u/pdfs/191212_qualtrics_successfactors_roadmap.pdf
TechTarget: What capabilities does Qualtrics EmployeeXM offer?: https://www.techtarget.com/enterprise-software/answer/What-capabilities-does-Qualtrics-EmployeeXM-offer
Qualtrics 360 terms (subject, evaluator, directory, administrator roles, workflows, waves) come from the Qualtrics Support page you referenced.
SAP and Qualtrics product names, packaging and integration options change often. Validate every product option with SAP and Qualtrics before committing.
Use-case fit, plan and risk ratings are our own judgement, not vendor statements.