## Read Me
Qualtrics Employee Experience Scoping Questionnaire
SAP SuccessFactors (Employee Central and PMGM live) + Qualtrics EX ¦ Go-live target in 3-4 months ¦ Prepared 28 Oct 2026
Client | [Client name]
Prepared by | [Consultant / firm]
Purpose | Gather the information needed to scope, size and sequence a Qualtrics Employee Experience (EX) implementation alongside SAP SuccessFactors, so the project can reach go-live in 3-4 months.
Context we assume | Employee Central and Performance & Goals (PMGM) are live. Other SuccessFactors modules are upcoming and some may go live in the same window. Treat every assumption here as a question to confirm.
How to use | 1) Start with the Use Case Map and mark each use case Wave 1 / Phase 2 / Out. 2) Answer the Questionnaire tab, starting with rows marked with a star (kick-off questions). 3) Complete the SF Module Readiness and Data Inventory tabs. 4) Review the 16-week plan and risks. Work in the yellow cells.
Priority | P1 = must answer to avoid blocking design or build. P2 = should answer before build. P3 = nice to have or Phase 2.
Needed by | Week 2 = needed in discovery. Week 4 = needed to finish design. Week 8 = needed before build completes. Post go-live = can follow launch.
Status values | Not started, In progress, Answered, Follow-up needed, Not applicable. The Summary tab counts these automatically.
Colour key | Yellow fill = cell for the client to complete. Blue text = date or number input you may change. Black text = formula or fixed content.
Product caution | SAP and Qualtrics product names, packaging and integration options change often. Where a question mentions a product option, treat it as something to validate with SAP and Qualtrics, not as a commitment.
Sources | See the Sources tab. Qualtrics 360 terms (subject, evaluator, directory, administrator types, workflows, waves) come from the Qualtrics Support page you provided.
Example of a completed row
ID | LCE-05
Question | How should exit surveys work: which exit types are included, and should they be sent before or after the last day?
Client response (example) | Resignation and retirement only; dismissal and contract end excluded. Send 3 days after last working day to personal email; HR owns the exit programme.
Status (example) | Answered
Respondent (example) | Priya Menon, Head of HR Operations
Follow-up (example) | Confirm personal-email consent wording with Legal by end of Week 3.

## Summary
Progress Summary
All figures calculate from the Questionnaire tab.
Section | Questions | P1 questions | Answered / N/A | Open | % complete | P1 still open
Project Context & Objectives | 11 | 8 | 0 | 11 | 0% | 8
Use-Case Selection & Prioritisation | 9 | 6 | 0 | 9 | 0% | 6
Licensing, Commercials & Contracting | 8 | 5 | 0 | 8 | 0% | 5
Employee Engagement Survey | 11 | 7 | 0 | 11 | 0% | 7
Pulse & Ad Hoc Listening | 8 | 3 | 0 | 8 | 0% | 3
Lifecycle Moments: Onboarding, Exit & Candidate | 14 | 8 | 0 | 14 | 0% | 8
360 / Multi-Rater Feedback | 14 | 8 | 0 | 14 | 0% | 8
Manager Effectiveness & Action Planning | 9 | 3 | 0 | 9 | 0% | 3
Employee Technology Experience | 7 | 1 | 0 | 7 | 0% | 1
Survey Content, Scales & Languages | 10 | 5 | 0 | 10 | 0% | 5
SuccessFactors Integration & Architecture | 15 | 10 | 0 | 15 | 0% | 10
Employee Data, Hierarchy & Attributes | 13 | 10 | 0 | 13 | 0% | 10
Reporting, Dashboards & Analytics (incl. AI) | 11 | 3 | 0 | 11 | 0% | 3
Security, Privacy & Compliance | 12 | 10 | 0 | 12 | 0% | 10
Roles, Access & Governance | 8 | 5 | 0 | 8 | 0% | 5
Communications, Change & Adoption | 10 | 5 | 0 | 10 | 0% | 5
Upcoming SuccessFactors Modules & Sequencing | 10 | 6 | 0 | 10 | 0% | 6
Delivery, Timeline, Testing & Support | 12 | 8 | 0 | 12 | 0% | 8
Success Measures & Operating Model | 8 | 2 | 0 | 8 | 0% | 2
Total | 200 | 113 | 0 | 200 | 0% | 113
By priority
Priority | Questions | Answered / N/A | Open
P1 - Must answer | 113 | 0 | 113
P2 - Should answer | 78 | 0 | 78
P3 - Nice to have | 9 | 0 | 9
By needed-by milestone
Needed by | Questions | Answered / N/A | Open
Week 2 | 50 | 0 | 50
Week 4 | 82 | 0 | 82
Week 8 | 53 | 0 | 53
Post go-live | 15 | 0 | 15

## Use Case Map
Use Case Map
Mark each use case for scope. The 'Fit for 3-4 month window' column is our starting hypothesis, to be challenged in discovery.
Use case | What it covers | Typical SuccessFactors trigger / data | Depends on | Fit for 3-4 month window | Why (hypothesis) | Scope decision | Business owner | Audience / population | Annual volume | Comments
Annual Engagement | Census survey of engagement, drivers and manager effectiveness with hierarchy-based reporting. | EC person, job and organisation data; reporting lines | EC only (live) | High | Needs EC data only; the biggest effort is content, anonymity design and reporting roles.
Pulse & Ad Hoc | Short recurring or event-driven surveys, including a SuccessFactors adoption pulse. | EC participant file; optional SF home-page embed | EC only (live) | High | Reuses the engagement foundation; quickest visible value.
Onboarding | Surveys at set days after hire for new hire, manager and buddy. | EC hire date, position start, manager, event reason | EC hire events; richer if SF Onboarding is live | Medium-High | Trigger works from EC; check hiring volumes, event reasons and email availability before day one.
Exit | Leaver feedback and attrition drivers, before or after the last day. | EC termination event, termination date, reason, contact data | EC termination events; offboarding process | Medium-High | Needs reliable termination data and a personal-contact policy; legal sensitivity is high.
Candidate Experience | Feedback from applicants across hiring stages. | Recruiting stages, requisition and applicant data | SF Recruiting (planned) | Low-Medium | Depends on Recruiting being live and on applicant-privacy rules; usually a Phase 2 candidate.
360 / Multi-Rater | Subjects receive feedback from self and evaluators; workflows can be predefined, nominated or open. | EC reporting lines, subject and evaluator lists, competency model | EC; PMGM overlap decision | Medium | Needs competency content, rater workflow and a decision against PMGM multi-rater; plan waves.
Manager Effectiveness & Action Planning | Manager dashboards, upward feedback and tracked action plans. | EC manager hierarchy; engagement results | Engagement or pulse results | Medium-High | Builds on engagement; the key risks are small-team anonymity and manager capability.
Employee Technology Experience | Feedback on tools and services, including SuccessFactors itself. | EC participants; optional ITSM events | Optional ITSM integration | Medium | SF-adoption pulse is a quick win; ITSM integration is Phase 2.
Internal Moves & Return from Leave | Surveys after promotion, transfer, leave return or manager change. | EC event reasons, status changes | EC events; data quality | Low-Medium | Same mechanics as onboarding; usually follows once triggers are proven.
Well-Being & Inclusion | Targeted surveys on well-being, belonging and inclusion. | EC demographics where permitted | Legal approval for sensitive data | Medium | Content and legal review dominate; the platform work is light.
Change & Project Pulses | Rapid feedback on restructuring, policy change or return-to-office. | EC participant selection | EC only (live) | High | Easy once the foundation exists; needs governance to avoid fatigue.

## Questionnaire
Scoping Questionnaire
200 questions across 19 sections. Filter by section, use case, priority, owner or needed-by. Complete the yellow columns.
ID | Section | Use case(s) | Question | Why we ask / guidance | Response type | Priority | Kick-off | Primary owner | Needed by | Client response | Status | Respondent | Follow-up / notes
CTX-01 | Project Context & Objectives | ALL | What are the top three business outcomes you expect from Qualtrics EX (for example lower regretted attrition, higher engagement, better onboarding, stronger managers, SuccessFactors adoption)? Please rank them. | Outcomes decide which use cases go first and how success is judged. | List / table | P1 - Must answer | ★ | Executive Sponsor | Week 2 |  | Not started
CTX-02 | Project Context & Objectives | ALL | Who is the executive sponsor, and what decision rights do they hold over scope, budget and the go-live date? | Avoids stalled decisions in a 3-4 month window. | Free text | P1 - Must answer | ★ | Executive Sponsor | Week 2 |  | Not started
CTX-03 | Project Context & Objectives | ALL | Which employee listening tools, vendors and programmes run today (engagement, pulse, onboarding, exit, 360)? Please share the last 24 months of results, response rates and survey instruments. | Gives baselines and reusable content. Qualtrics itself advises gathering previous reports as a reference point. | List / table | P1 - Must answer | ★ | HR / People Leadership | Week 2 |  | Not started
CTX-04 | Project Context & Objectives | ALL | Which existing survey programmes must be replaced, kept, or run in parallel at go-live? | Drives migration, trend continuity and communication. | Single choice | P1 - Must answer |  | HR / People Leadership | Week 4 |  | Not started
CTX-05 | Project Context & Objectives | ALL | Workforce profile: headcount, countries, legal entities, worker types (employees, contingent, interns), share of shift or deskless staff, and languages spoken. | Sizes licences, languages, delivery channels and test scope. | List / table | P1 - Must answer | ★ | HR / People Leadership | Week 2 |  | Not started
CTX-06 | Project Context & Objectives | ALL | Is the go-live date fixed? What drives it (contract start, board commitment, business event) and what is the cost of moving it by four weeks? | Tells us whether to cut scope or move the date when trade-offs appear. | Free text | P1 - Must answer | ★ | Executive Sponsor | Week 2 |  | Not started
CTX-07 | Project Context & Objectives | ALL | Which other programmes compete for the same HR, HRIS, IT and communications people over the next four months (other SF module go-lives, payroll cycles, M&A, restructuring)? | Capacity clashes are a leading cause of slippage. | List / table | P1 - Must answer |  | Project / PMO | Week 2 |  | Not started
CTX-08 | Project Context & Objectives | ALL | Who will own EX after go-live (HR, People Analytics, IT, Internal Comms) and how large is the run team? | The design must match the team that will operate it. | Free text | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
CTX-09 | Project Context & Objectives | ALL | Is there an EX framework, employee value proposition or people strategy that survey content and dashboards should align to? | Keeps content and reporting consistent with strategy. | Free text | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
CTX-10 | Project Context & Objectives | ALL | What has worked or failed in past listening efforts (low participation, survey fatigue, no visible action, trust issues)? | Prevents repeating known failures. | Free text | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
CTX-11 | Project Context & Objectives | ALL | Is Qualtrics already used elsewhere in the organisation (CX, brand, research)? If so, share tenant details, data centre and existing administrators. | Lets us reuse existing tenant, SSO and security approvals. | List / table | P1 - Must answer | ★ | IT / Architecture | Week 2 |  | Not started
USE-01 | Use-Case Selection & Prioritisation | ALL | For each use case on the Use Case Map tab, mark Wave 1 (go-live), Phase 2, or Out of scope. | The core scoping decision; everything else follows from it. | List / table | P1 - Must answer | ★ | Executive Sponsor | Week 2 |  | Not started
USE-02 | Use-Case Selection & Prioritisation | ALL | For each in-scope use case, who is the business owner, who is the audience, and what decision will the data drive? | A use case without an owner and a decision becomes shelfware. | List / table | P1 - Must answer |  | HR / People Leadership | Week 2 |  | Not started
USE-03 | Use-Case Selection & Prioritisation | ALL | If only one or two use cases could be live in 3-4 months, which would they be and why? | Forces a realistic minimum viable launch. | Free text | P1 - Must answer | ★ | Executive Sponsor | Week 2 |  | Not started
USE-04 | Use-Case Selection & Prioritisation | ONB, EXT, CAN | Which use cases depend on SuccessFactors modules that are not yet live, and could they start with a file-based or manual trigger? | Lets lifecycle use cases launch without waiting for every module. | Free text | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 4 |  | Not started
USE-05 | Use-Case Selection & Prioritisation | ALL | Beyond the standard list, are there other use cases (M&A integration, return-to-office, restructuring, safety culture, well-being, inclusion, SuccessFactors adoption)? | Surfaces ad hoc needs early so the design stays flexible. | Multi-select | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
USE-06 | Use-Case Selection & Prioritisation | ALL | Which populations are in scope for each use case (all employees, countries, entities, job families, new joiners, leavers, contingent workers)? | Determines the participant file, licences and legal review. | List / table | P1 - Must answer |  | HR / People Leadership | Week 4 |  | Not started
USE-07 | Use-Case Selection & Prioritisation | ALL | How often must each use case run (annual, quarterly, event-triggered, always-on), and what are the blackout periods (year-end, payroll, appraisal cycles, local holidays)? | Builds the listening calendar and avoids fatigue and clashes. | List / table | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
USE-08 | Use-Case Selection & Prioritisation | ALL | Will one listening calendar govern engagement, pulse and lifecycle surveys, and who owns it? | Caps total surveys per employee and avoids overlap. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
USE-09 | Use-Case Selection & Prioritisation | 360, ENG, PLS | Which surveys should be tied to the SF PMGM cycle (for example 360 feedback inside the performance cycle, or a post-review pulse)? | Aligns timing and avoids stacking requests on managers. | Free text | P2 - Should answer |  | Talent & L&D | Week 4 |  | Not started
COM-01 | Licensing, Commercials & Contracting | ALL | How is Qualtrics EX contracted: SAP Endorsed Apps agreement, directly with Qualtrics, or via a reseller? Which products or SKUs (Engagement, Pulse, Onboarding, Exit, 360, Lifecycle, Employee Technology Experience)? | Licensed products set what can be configured and when. SAP and Qualtrics announced an Endorsed Apps route in January 2025. | Single choice | P1 - Must answer | ★ | Finance / Procurement | Week 2 |  | Not started
COM-02 | Licensing, Commercials & Contracting | ALL | What are the licensed participant counts per product, and the contract start date and term? Does the licence start before the build begins? | A late licence start blocks tenant access and build. | Number | P1 - Must answer |  | Finance / Procurement | Week 2 |  | Not started
COM-03 | Licensing, Commercials & Contracting | ALL | Is the Qualtrics tenant (brand) already provisioned, and in which data centre region? | Region drives data residency and is hard to change later. | Yes / No | P1 - Must answer | ★ | IT / Architecture | Week 2 |  | Not started
COM-04 | Licensing, Commercials & Contracting | RPT | Are AI features (Qualtrics Assist, text analytics, conversational feedback) licensed, and permitted under your internal AI policy? | AI features may need separate approval. | Yes / No | P2 - Should answer | ★ | IT / Architecture | Week 4 |  | Not started
COM-05 | Licensing, Commercials & Contracting | ALL | What budget is approved for implementation, change management, translation and run costs (admin effort, partner support)? | Sets realistic scope. | Free text | P2 - Should answer |  | Finance / Procurement | Week 4 |  | Not started
COM-06 | Licensing, Commercials & Contracting | ALL | Who is the implementation partner, and which SAP and Qualtrics contacts (account executives, solution architects) are engaged? | Shows who can unblock licence, tenant and integration questions. | Free text | P1 - Must answer | ★ | Project / PMO | Week 2 |  | Not started
COM-07 | Licensing, Commercials & Contracting | ALL | What is the status of procurement, vendor risk assessment and data processing agreements for Qualtrics, and how long do these normally take? | Security and legal reviews can exceed eight weeks. | Free text | P1 - Must answer | ★ | Security & Privacy | Week 2 |  | Not started
COM-08 | Licensing, Commercials & Contracting | INT | Are there other costs to plan for: integration middleware (SAP BTP / Integration Suite), SSO, premium support, benchmarks? | Avoids late surprises. | List / table | P2 - Should answer |  | Finance / Procurement | Week 4 |  | Not started
ENG-01 | Employee Engagement Survey | ENG | Is there an existing engagement model or index (composite index, eNPS, drivers)? Must trend continuity with historical results be preserved? | Changing items breaks year-on-year comparison. | Free text | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
ENG-02 | Employee Engagement Survey | ENG | Will you use the Qualtrics best-practice engagement library, a custom model, or a hybrid? Who approves final content? | Decides build effort, translation scope and approval path. | Single choice | P1 - Must answer |  | HR / People Leadership | Week 4 |  | Not started
ENG-03 | Employee Engagement Survey | ENG | Census or sample? What participation target do you set, and what was achieved last time? | Sets licence volume, reminder strategy and success KPI. | Free text | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
ENG-04 | Employee Engagement Survey | ENG | Which results cuts are required (org unit, location, job level, tenure, age band, gender, manager)? What is the minimum group size for reporting? | Drives data attributes needed from EC and the anonymity threshold. | List / table | P1 - Must answer | ★ | People Analytics | Week 4 |  | Not started
ENG-05 | Employee Engagement Survey | ENG | Will the survey be anonymous or confidential? Will SF attributes be attached to responses, and how will employees be told? | The promise made to employees must match the technical design. | Single choice | P1 - Must answer | ★ | Legal / DPO / Employee Relations | Week 4 |  | Not started
ENG-06 | Employee Engagement Survey | ENG | Is benchmarking required (internal, industry, external)? Against which peer groups? | Determines licensed benchmark content and comparisons. | Free text | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
ENG-07 | Employee Engagement Survey | ENG | Who sees results (executives, HRBPs, all people managers), and when? What is the cascade process? | Defines roles, dashboard design and release gates. | List / table | P1 - Must answer |  | HR / People Leadership | Week 8 |  | Not started
ENG-08 | Employee Engagement Survey | ENG | How will open-text comments be handled: languages, redaction of names, and escalation of sensitive content (harassment, safety)? | Duty-of-care and anonymity obligations. | Free text | P1 - Must answer | ★ | Legal / DPO / Employee Relations | Week 8 |  | Not started
ENG-09 | Employee Engagement Survey | ENG, MGR | What are managers expected to do with results (action plans, deadlines, tracking)? Should plans link to SF goals or development plans? | Closing the loop is what makes engagement credible. | Free text | P1 - Must answer | ★ | HR / People Leadership | Week 8 |  | Not started
ENG-10 | Employee Engagement Survey | ENG | What survey window and reminder pattern are planned, and how will frontline or deskless staff take part (mobile, kiosk, QR code, personal links)? | Participation fails when access is not designed in. | Free text | P2 - Should answer |  | Internal Communications | Week 8 |  | Not started
ENG-11 | Employee Engagement Survey | ENG | Do you expect to link engagement to attrition, performance (PMGM ratings) or other HR outcomes, and is that permitted by policy and employee representatives? | Joining survey and HR data is valuable but needs legal and trust safeguards. | Free text | P2 - Should answer | ★ | People Analytics | Post go-live |  | Not started
PLS-01 | Pulse & Ad Hoc Listening | PLS | Which pulse programmes do you need (always-on, quarterly, topic-based, post-event, manager pulse)? | Defines templates, licences and cadence. | List / table | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
PLS-02 | Pulse & Ad Hoc Listening | PLS | Who may launch a pulse (central HR only, or delegated to HRBPs and managers)? What caps prevent fatigue (maximum surveys per employee per quarter)? | Governance prevents survey overload. | Free text | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
PLS-03 | Pulse & Ad Hoc Listening | PLS | How will respondents be sampled (full population, random sample, rotating cohorts)? | Affects participant lists and statistical validity. | Free text | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
PLS-04 | Pulse & Ad Hoc Listening | PLS | Who curates the standard pulse question bank, and what is the target length (items and minutes)? | Keeps pulses short and comparable. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
PLS-05 | Pulse & Ad Hoc Listening | PLS | Which delivery channels are needed: email, SF home page or Engagement card, MS Teams, Slack, SMS, mobile, QR codes? | Channels determine integration effort and response rates. | Multi-select | P1 - Must answer | ★ | Internal Communications | Week 4 |  | Not started
PLS-06 | Pulse & Ad Hoc Listening | PLS, ETX | For ad hoc, event-driven pulses (restructuring, policy change, SuccessFactors go-live), what approval workflow and turnaround time are expected? | Speed versus control trade-off. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
PLS-07 | Pulse & Ad Hoc Listening | PLS | Should low scores trigger real-time alerts or cases to HRBPs or managers? Which case or ticketing system would receive them? | Defines workflow and integration scope. | Free text | P2 - Should answer | ★ | HR / People Leadership | Post go-live |  | Not started
PLS-08 | Pulse & Ad Hoc Listening | PLS | Who sees pulse results, at what minimum group size, and how quickly after close? | Sets expectations and dashboard design. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
LCE-01 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB, EXT, CAN | Which lifecycle moments are in scope: candidate, pre-boarding, Day 1 / 30 / 90 / 180, probation end, promotion, transfer, return from leave, manager change, exit (voluntary or involuntary), alumni? | Each moment needs a trigger, template and owner. | Multi-select | P1 - Must answer | ★ | HR / People Leadership | Week 2 |  | Not started
LCE-02 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB, EXT | For each moment, what is the EC trigger (hire date, position start, event reason, employment status, termination date)? Which event reasons apply? | Triggers must be reliable and mapped to configured event reasons. | List / table | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 2 |  | Not started
LCE-03 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB | Is SAP SuccessFactors Onboarding (or another tool) live at go-live? If not, what is the system of record for new-hire tasks and data? | Determines whether onboarding surveys can use task or milestone data. | Single choice | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 2 |  | Not started
LCE-04 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB | What are the monthly hiring volumes by country, and what survey cadence is wanted (days since hire) for new hire, manager and buddy? | Sizes the programme and tells us if results will reach reportable group sizes. | Number | P1 - Must answer | ★ | Talent Acquisition | Week 4 |  | Not started
LCE-05 | Lifecycle Moments: Onboarding, Exit & Candidate | EXT | How should exit surveys work: which exit types are included (resignation, retirement, dismissal, contract end), and should they be sent before or after the last day? | Exit timing and exclusions are sensitive and legal-critical. | Free text | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
LCE-06 | Lifecycle Moments: Onboarding, Exit & Candidate | EXT | After offboarding, how will leavers be reached (personal email) and what are the policy and legal limits on holding that data and on alumni contact? | Corporate email is often disabled at exit. | Free text | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
LCE-07 | Lifecycle Moments: Onboarding, Exit & Candidate | EXT | Will a self-service survey complement or replace HR-led exit interviews? Is manager input about the leaver required? | Defines the exit experience and data model. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
LCE-08 | Lifecycle Moments: Onboarding, Exit & Candidate | CAN | Is Recruiting Management in scope and live? At which stages should candidate surveys trigger (applied, interviewed, offered, declined, hired), and what applicant-privacy limits apply? | Candidate data often sits in a different system with different privacy rules. | Free text | P2 - Should answer |  | Talent Acquisition | Week 8 |  | Not started
LCE-09 | Lifecycle Moments: Onboarding, Exit & Candidate | LCE | Are surveys needed for internal moves, promotions, return from leave or manager change? | Candidate Phase 2 moments. | Multi-select | P3 - Nice to have |  | HR / People Leadership | Post go-live |  | Not started
LCE-10 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB, EXT | When a new hire or leaver raises a serious issue (harassment, safety, discrimination), who is notified, how fast, and what happens to anonymity? | Duty-of-care protocol must exist before launch. | Free text | P1 - Must answer | ★ | Legal / DPO / Employee Relations | Week 4 |  | Not started
LCE-11 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB, EXT, MGR | Do managers see onboarding and exit results for their teams, and under what anonymity rules? | Balances insight and confidentiality. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
LCE-12 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB, EXT | How reliable are hire and termination dates, business email and manager assignment in EC today? Are back-dated, future-dated or mass-uploaded records common? | Lifecycle triggers fire on this data; poor quality means missed or wrong surveys. | Free text | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 2 |  | Not started
LCE-13 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB, EXT | What annual volumes do you expect for each lifecycle type? | Sizes testing and licences. | Number | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
LCE-14 | Lifecycle Moments: Onboarding, Exit & Candidate | ONB, EXT | Which countries have specific rules for onboarding or exit surveys (consultation, consent, restricted data)? | Avoids country-level blocks on go-live. | Free text | P2 - Should answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
360-01 | 360 / Multi-Rater Feedback | 360 | Is 360 in scope for go-live? What is its purpose: development only, leadership assessment, talent-review input, or performance input? | Purpose sets confidentiality, report design and legal review. | Single choice | P1 - Must answer | ★ | Talent & L&D | Week 2 |  | Not started
360-02 | 360 / Multi-Rater Feedback | 360 | SF PMGM is already live. Does it already run multi-rater or 360 feedback? Which tool will be the system of record for 360 (Qualtrics 360 or PMGM), and what drives the choice? | Avoids two competing 360 processes and duplicated rater fatigue. | Single choice | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 2 |  | Not started
360-03 | 360 / Multi-Rater Feedback | 360 | Who are the subjects (all managers, senior leaders, high potentials)? How many, and how often (annual, cycle-aligned)? | Sizes licences and workload. | List / table | P1 - Must answer |  | Talent & L&D | Week 4 |  | Not started
360-04 | 360 / Multi-Rater Feedback | 360 | Which workflow model applies: predefined subject-evaluator pairs, subject nominates from a predefined list, or open nomination? Is manager approval of raters required? | These are the standard Qualtrics 360 workflows and each needs different data. | Single choice | P1 - Must answer | ★ | Talent & L&D | Week 4 |  | Not started
360-05 | 360 / Multi-Rater Feedback | 360 | Which rater categories (manager, peers, direct reports, skip-level, customers, external) and what minimum raters per category before results show? | Anonymity depends on minimums. | List / table | P1 - Must answer |  | Talent & L&D | Week 4 |  | Not started
360-06 | 360 / Multi-Rater Feedback | 360 | Should the project run in waves (nominations, evaluations, report release), and how long should each wave last? | Qualtrics recommends waves for 360 projects; durations drive the calendar. | Free text | P2 - Should answer |  | Talent & L&D | Week 8 |  | Not started
360-07 | 360 / Multi-Rater Feedback | 360 | Is there a leadership competency model? How many competencies and items, which rating scale, which open-ended questions, which scoring categories, and which translations? | Question set and scoring categories must be final before build. | List / table | P1 - Must answer | ★ | Talent & L&D | Week 4 |  | Not started
360-08 | 360 / Multi-Rater Feedback | 360 | How will subject and evaluator data be derived from EC: reporting lines, dotted-line or matrix managers, project teams? | Rater lists are the main data dependency of 360. | Free text | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 4 |  | Not started
360-09 | 360 / Multi-Rater Feedback | 360 | What should subject reports contain, and who sees them (subject, manager, HRBP, coach)? Are norm groups or benchmarks needed? | Drives report design and access rules. | List / table | P2 - Should answer |  | Talent & L&D | Week 8 |  | Not started
360-10 | 360 / Multi-Rater Feedback | 360 | How do 360 results flow to development plans (SF Succession & Development, Learning) or stay outside SF? | Defines integration and confidentiality. | Free text | P2 - Should answer |  | Talent & L&D | Week 8 |  | Not started
360-11 | 360 / Multi-Rater Feedback | 360 | Who writes invitation and reminder messages, in which languages, and who coaches subjects on results? | Messaging and coaching drive trust and quality. | Free text | P2 - Should answer |  | Talent & L&D | Week 8 |  | Not started
360-12 | 360 / Multi-Rater Feedback | 360 | Are external evaluators (customers, vendors) or contingent workers included, and how is their data handled? | External participants have different data and access needs. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
360-13 | 360 / Multi-Rater Feedback | 360 | May 360 results be used in talent, promotion or pay decisions? What do the legal team and employee representatives say? | Use of results changes legal and consultation requirements. | Free text | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
360-14 | 360 / Multi-Rater Feedback | 360 | Which subjects will pilot, and when? What success criteria would let you scale? | A small pilot lowers launch risk. | Free text | P2 - Should answer |  | Talent & L&D | Week 8 |  | Not started
MGR-01 | Manager Effectiveness & Action Planning | MGR | Is manager effectiveness a named use case (upward feedback, manager pulse, manager scorecard)? | Decides content and reporting scope. | Yes / No | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
MGR-02 | Manager Effectiveness & Action Planning | MGR | What must managers do after results arrive: required action plans, deadlines, tracking and nudges? | Defines the action-planning module scope. | Free text | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
MGR-03 | Manager Effectiveness & Action Planning | MGR | Do you have manager development content (internal or from Qualtrics) to recommend alongside results? Should it link to SF Learning? | Turns insight into help. | Free text | P2 - Should answer |  | Talent & L&D | Week 8 |  | Not started
MGR-04 | Manager Effectiveness & Action Planning | MGR | How is a manager defined for reporting (direct reports, full hierarchy roll-up, matrix)? What happens when a manager has fewer reports than the minimum group size? | Small teams are the most common anonymity problem. | Free text | P1 - Must answer | ★ | People Analytics | Week 4 |  | Not started
MGR-05 | Manager Effectiveness & Action Planning | MGR | What follow-up applies to low-scoring teams (HRBP involvement, targeted support)? | Defines escalation rules. | Free text | P2 - Should answer | ★ | HR / People Leadership | Week 8 |  | Not started
MGR-06 | Manager Effectiveness & Action Planning | MGR | Who tracks action-plan completion, and how is it reported to executives? | Accountability for outcomes. | Free text | P2 - Should answer |  | HR / People Leadership | Post go-live |  | Not started
MGR-07 | Manager Effectiveness & Action Planning | MGR | Should action plans link to SF goals, PMGM or development plans? | Decides the return integration to SF. | Free text | P2 - Should answer |  | HRIS / SuccessFactors Lead | Post go-live |  | Not started
MGR-08 | Manager Effectiveness & Action Planning | MGR | How many managers need access, and will they use dashboards (SSO) or receive PDFs or emails? | Drives licence, role and SSO design. | Number | P1 - Must answer | ★ | IT / Architecture | Week 4 |  | Not started
MGR-09 | Manager Effectiveness & Action Planning | MGR | Who will train managers to read results and run team discussions? Are conversation guides needed? | Manager capability decides whether action happens. | Free text | P2 - Should answer |  | Talent & L&D | Week 8 |  | Not started
ETX-01 | Employee Technology Experience | ETX | Is Employee Technology Experience in scope? Which tools and services (laptops, VPN, collaboration, service desk, SuccessFactors itself)? | Decides if IT-side stakeholders join discovery. | Yes / No | P2 - Should answer | ★ | IT / Architecture | Week 4 |  | Not started
ETX-02 | Employee Technology Experience | ETX | Who owns it (CIO, service desk, digital workplace) and is there sponsor and budget? | Needs an owner outside HR. | Free text | P2 - Should answer | ★ | IT / Architecture | Week 4 |  | Not started
ETX-03 | Employee Technology Experience | ETX | Which ITSM or ticketing tool is in use (ServiceNow, Jira, other)? Should low scores create tickets? | Closing the loop on IT issues needs integration. | Single choice | P2 - Should answer | ★ | IT / Architecture | Week 8 |  | Not started
ETX-04 | Employee Technology Experience | ETX | What triggers these surveys: ticket closure, device refresh, a new SF release, or a periodic cycle? | Defines event sources. | Free text | P2 - Should answer |  | IT / Architecture | Week 8 |  | Not started
ETX-05 | Employee Technology Experience | ETX, PLS | Do you want to measure employee and manager experience of SuccessFactors itself (EC self-service, PMGM, new modules) right after go-live? | Fast win that also supports adoption. | Yes / No | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 4 |  | Not started
ETX-06 | Employee Technology Experience | ETX | Is device, location or application data beyond EC needed for segmentation? | Adds data sources. | Free text | P3 - Nice to have |  | IT / Architecture | Post go-live |  | Not started
ETX-07 | Employee Technology Experience | ETX | Which technology KPIs are targeted (satisfaction, effort, time-to-resolve)? | Aligns metrics. | Free text | P3 - Nice to have |  | IT / Architecture | Post go-live |  | Not started
SUR-01 | Survey Content, Scales & Languages | ALL | Which languages are required per use case? What is the source language, translation method (human, machine plus review) and who validates? | Translation lead time can decide the go-live date. | List / table | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
SUR-02 | Survey Content, Scales & Languages | ALL | Which rating scales and wording standards must be used (5, 7 or 10 point, agree/disagree, eNPS) to stay comparable with history? | Standardising early avoids rework. | Single choice | P1 - Must answer | ★ | People Analytics | Week 4 |  | Not started
SUR-03 | Survey Content, Scales & Languages | ALL | Which demographic attributes come from SF (hidden metadata) and which are asked? Are any categories restricted in certain countries (gender, ethnicity, age, disability)? | Legal and privacy constraints vary by country. | Free text | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
SUR-04 | Survey Content, Scales & Languages | ALL | What privacy notice, consent text and mandatory statements must appear on each survey? | Must be reviewed before build. | Free text | P1 - Must answer | ★ | Legal / DPO / Employee Relations | Week 4 |  | Not started
SUR-05 | Survey Content, Scales & Languages | ALL | What branding is required (logo, colours, tone) and which accessibility standard (for example WCAG) must surveys meet? | Quick to define now and costly later. | Free text | P2 - Should answer |  | Internal Communications | Week 8 |  | Not started
SUR-06 | Survey Content, Scales & Languages | ALL | What accessibility needs exist (screen readers, low bandwidth, shift workers, kiosks)? | Ensures every employee can respond. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
SUR-07 | Survey Content, Scales & Languages | ALL | What survey length targets apply, and who signs off on content? | Controls fatigue and approval time. | Free text | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
SUR-08 | Survey Content, Scales & Languages | ALL | Will you use Qualtrics best-practice libraries (engagement, onboarding, exit, 360, well-being, candidate) as the baseline, and how much customisation is allowed? | Libraries speed delivery; customisation adds testing and translation. | Single choice | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
SUR-09 | Survey Content, Scales & Languages | ALL | Which scoring conventions apply (favourable %, mean, top-box)? | Keeps analytics consistent. | Free text | P3 - Nice to have |  | People Analytics | Week 8 |  | Not started
SUR-10 | Survey Content, Scales & Languages | PLS, ENG | Would you accept AI-assisted follow-up questions on vague comments (conversational feedback)? | Needs policy approval. | Free text | P3 - Nice to have |  | Legal / DPO / Employee Relations | Week 8 |  | Not started
INT-01 | SuccessFactors Integration & Architecture | ALL | Describe the SuccessFactors landscape: instances (test, preview, production), data centre, EC release status, identity provider and SSO. | Foundation for integration and authentication design. | List / table | P1 - Must answer | ★ | IT / Architecture | Week 2 |  | Not started
INT-02 | SuccessFactors Integration & Architecture | ALL | What is the preferred method for sending EC employee data to Qualtrics: pre-packaged SF extension, SFTP file, API or Integration Center, or SAP BTP Integration Suite? Any constraints? | Selects the integration pattern and drives effort. | Single choice | P1 - Must answer | ★ | IT / Architecture | Week 2 |  | Not started
INT-03 | SuccessFactors Integration & Architecture | ALL | Do you have SAP BTP / Integration Suite today? Who has the skills and capacity to build and run the integration? | Capacity is the main schedule risk for integration. | Free text | P1 - Must answer |  | IT / Architecture | Week 2 |  | Not started
INT-04 | SuccessFactors Integration & Architecture | ALL | How often must data sync (daily full, daily delta, near real time)? Which fields need near-real-time updates (hire for onboarding, termination for exit)? | Sync frequency decides architecture. | Single choice | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 4 |  | Not started
INT-05 | SuccessFactors Integration & Architecture | ONB, EXT | How will EC events (hire, transfer, termination) trigger surveys: SF Intelligent Services events, Integration Center, or scheduled delta files? Is Intelligent Services enabled? | Event triggers are the heart of lifecycle surveys. | Free text | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 4 |  | Not started
INT-06 | SuccessFactors Integration & Architecture | PLS, ETX | Do surveys need to appear inside SF (home page tile, Engagement card, mobile app)? On which SF home page version? | Embedded delivery improves response and adoption. | Yes / No | P2 - Should answer | ★ | HRIS / SuccessFactors Lead | Week 8 |  | Not started
INT-07 | SuccessFactors Integration & Architecture | MGR, RPT | Should results or action plans flow back to SF (development plans, goals, talent profile) or to a data warehouse (SAC, Datasphere, BW)? | Return flows add scope and security review. | Free text | P2 - Should answer |  | IT / Architecture | Post go-live |  | Not started
INT-08 | SuccessFactors Integration & Architecture | ALL | Which identity standard will be used for employee access (SAML or OIDC, which IdP)? What is the fallback for employees without SSO? | Access design affects frontline reach and security approval. | Single choice | P1 - Must answer |  | Security & Privacy | Week 2 |  | Not started
INT-09 | SuccessFactors Integration & Architecture | ALL | How many Qualtrics sandbox and production environments are needed, how often is SF preview refreshed, and what is the policy on test data (anonymised or real)? | Environments and test data decide test quality and compliance. | Free text | P1 - Must answer |  | IT / Architecture | Week 4 |  | Not started
INT-10 | SuccessFactors Integration & Architecture | ALL | What API user, OAuth, IP allow-list and permission roles will the integration need, and who approves them? | Integration security approvals take time. | Free text | P1 - Must answer |  | Security & Privacy | Week 4 |  | Not started
INT-11 | SuccessFactors Integration & Architecture | ALL | Who monitors failed syncs, how will alerts be raised, and what SLA is expected? | Operational readiness for run. | Free text | P2 - Should answer |  | IT / Architecture | Week 8 |  | Not started
INT-12 | SuccessFactors Integration & Architecture | ALL | What architecture-board approvals and change-freeze windows apply in the next four months? | Freeze windows can block deployment. | Free text | P1 - Must answer | ★ | IT / Architecture | Week 2 |  | Not started
INT-13 | SuccessFactors Integration & Architecture | ALL | Is data needed from outside EC (Employee Central Payroll, time tracking, ITSM, other HR systems)? | Extra sources lengthen the build. | Free text | P2 - Should answer |  | HRIS / SuccessFactors Lead | Week 8 |  | Not started
INT-14 | SuccessFactors Integration & Architecture | ALL | Do firewalls or mail filters need allow-listing for Qualtrics survey links? How is email deliverability handled (sender domain, SPF, DKIM)? | Invitations landing in spam is a frequent launch problem. | Free text | P1 - Must answer |  | IT / Architecture | Week 4 |  | Not started
INT-15 | SuccessFactors Integration & Architecture | RPT | Do People Analytics or Workforce Analytics pipelines need to consume EX data? | Plans downstream data flows. | Free text | P3 - Nice to have |  | People Analytics | Post go-live |  | Not started
DAT-01 | Employee Data, Hierarchy & Attributes | ALL | Which EC fields are needed in Qualtrics (person, employment, job, organisation: legal entity, business unit, division, department, location, cost centre, job family, level, manager, position)? Please complete the Data Inventory tab. | The field list is the backbone of hierarchy, triggers and segmentation. | List / table | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 2 |  | Not started
DAT-02 | Employee Data, Hierarchy & Attributes | ALL | How complete and trusted is EC data (manager, email, location, job level)? Which known gaps exist? | Data quality problems surface as wrong survey populations. | Free text | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 2 |  | Not started
DAT-03 | Employee Data, Hierarchy & Attributes | ALL | Which organisational structure drives reporting (reporting line or organisation units)? How many levels and units exist? | Determines hierarchy build and dashboard roll-ups. | Free text | P1 - Must answer | ★ | People Analytics | Week 2 |  | Not started
DAT-04 | Employee Data, Hierarchy & Attributes | ALL | How are matrix, dotted-line, concurrent employment, global assignments and secondments handled? Which manager and organisation does each person report under? | These cases create duplicates and wrong roll-ups. | Free text | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 4 |  | Not started
DAT-05 | Employee Data, Hierarchy & Attributes | ALL | Which demographic attributes exist in EC and are approved for survey analysis (gender, age band, tenure, nationality, and so on)? | Needs privacy and legal approval. | List / table | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
DAT-06 | Employee Data, Hierarchy & Attributes | ALL | Who is eligible to be surveyed: active, on leave, notice period, contingent, part-time, future hires? What are the exclusion rules? | Eligibility rules define the participant file. | Free text | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
DAT-07 | Employee Data, Hierarchy & Attributes | ALL | What contact data is available: business email coverage, personal email, mobile number for deskless staff, preferred language? | Without contact data people cannot be invited. | List / table | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 4 |  | Not started
DAT-08 | Employee Data, Hierarchy & Attributes | ALL | Where should derived attributes (tenure band, age band, span of control) be calculated: EC, middleware or Qualtrics? | Avoids inconsistent definitions. | Free text | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
DAT-09 | Employee Data, Hierarchy & Attributes | ENG, PLS | Is there historical survey data or historical organisation snapshots to load for trend reporting? Format, volume and quality? | Historical loads need mapping effort. | Free text | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
DAT-10 | Employee Data, Hierarchy & Attributes | ALL | What retention periods apply per use case? How are leavers' data deletion and erasure requests handled? | Retention rules shape configuration. | Free text | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
DAT-11 | Employee Data, Hierarchy & Attributes | ALL | Are reorganisations planned between now and go-live, and how will hierarchy changes during a survey window be handled (snapshot or live)? | Mid-survey changes corrupt results. | Free text | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 2 |  | Not started
DAT-12 | Employee Data, Hierarchy & Attributes | ALL | Which unique identifier will be the key between EC and Qualtrics (person ID, user ID), and how will pseudonymisation be handled? | Key design is hard to change after build. | Single choice | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 2 |  | Not started
DAT-13 | Employee Data, Hierarchy & Attributes | ALL | Are there entities or populations not on EC (acquisitions, joint ventures, contractors)? Should they be included and from which source? | Scope and data source gap. | Free text | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
RPT-01 | Reporting, Dashboards & Analytics (incl. AI) | ALL | Which reporting audiences exist (executives, HRBPs, managers, employees, People Analytics) and what does each need to see? | Defines roles and dashboard scope. | List / table | P1 - Must answer | ★ | People Analytics | Week 4 |  | Not started
RPT-02 | Reporting, Dashboards & Analytics (incl. AI) | ALL | Which dashboard types are must-have: executive overview, manager dashboard, heat map, driver analysis, comparison, trend? | Controls build effort. | Multi-select | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
RPT-03 | Reporting, Dashboards & Analytics (incl. AI) | ALL | How will reports be distributed: dashboard login, scheduled email, PDF, embedded in SF? | Affects access model and SSO. | Multi-select | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
RPT-04 | Reporting, Dashboards & Analytics (incl. AI) | ALL | Who needs live response-rate tracking and at what granularity (without identifying respondents)? | Supports participation management. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
RPT-05 | Reporting, Dashboards & Analytics (incl. AI) | ALL | Which text analytics and AI summaries (Qualtrics Assist) are in scope, in which languages, and do Legal and employee representatives approve them? | AI on employee comments needs explicit approval. | Free text | P1 - Must answer | ★ | Legal / DPO / Employee Relations | Week 4 |  | Not started
RPT-06 | Reporting, Dashboards & Analytics (incl. AI) | ENG, PLS, 360 | Will survey data be combined with SF data (turnover, PMGM performance rating, promotion, tenure) for analysis? What safeguards apply? | Joined data is powerful and sensitive. | Free text | P1 - Must answer | ★ | People Analytics | Week 4 |  | Not started
RPT-07 | Reporting, Dashboards & Analytics (incl. AI) | ENG | Which internal targets and external benchmarks apply? | Defines reporting comparisons. | Free text | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
RPT-08 | Reporting, Dashboards & Analytics (incl. AI) | ALL | Do reports need local-language labels or corporate templates? | Template effort. | Free text | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
RPT-09 | Reporting, Dashboards & Analytics (incl. AI) | ALL | Will raw data go to a data warehouse or People Analytics, how often, and who holds access? | Extra export flows. | Free text | P2 - Should answer |  | People Analytics | Post go-live |  | Not started
RPT-10 | Reporting, Dashboards & Analytics (incl. AI) | ALL | What accessibility and mobile support is needed for dashboards? | Usability for all managers. | Free text | P2 - Should answer |  | People Analytics | Week 8 |  | Not started
RPT-11 | Reporting, Dashboards & Analytics (incl. AI) | ALL | Which custom metrics (eNPS, engagement index composition, attrition-risk index) need agreed definitions and owners? | Metric definitions must be fixed before dashboards. | List / table | P2 - Should answer | ★ | People Analytics | Week 4 |  | Not started
SEC-01 | Security, Privacy & Compliance | ALL | Where must employee data be stored and processed? Are there restrictions on cross-border transfer (EU, India, China, Middle East, other)? | Residency drives data-centre choice and legal basis. | List / table | P1 - Must answer | ★ | Legal / DPO / Employee Relations | Week 2 |  | Not started
SEC-02 | Security, Privacy & Compliance | ALL | Has a DPIA or privacy impact assessment been done or required? Who is the DPO and when must they be consulted? | Often a critical-path item. | Free text | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 2 |  | Not started
SEC-03 | Security, Privacy & Compliance | ALL | Which countries require works council, union or employee representative consultation, and what are the lead times? | Consultation can delay go-live by weeks or months. | List / table | P1 - Must answer | ★ | Legal / DPO / Employee Relations | Week 2 |  | Not started
SEC-04 | Security, Privacy & Compliance | ALL | What anonymity commitments apply: minimum group size, suppression of small groups, comment redaction, and who approves exceptions? | Anonymity breaches destroy trust. | Free text | P1 - Must answer | ★ | Legal / DPO / Employee Relations | Week 4 |  | Not started
SEC-05 | Security, Privacy & Compliance | ALL | What is the legal basis (legitimate interest or consent) and the required privacy notice wording for each country? | Needed before the first invitation. | Free text | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
SEC-06 | Security, Privacy & Compliance | ALL | Which EC attributes are classified sensitive or restricted? Are any prohibited from leaving EC? | Sets the data mapping scope. | Free text | P1 - Must answer |  | Security & Privacy | Week 4 |  | Not started
SEC-07 | Security, Privacy & Compliance | ALL | What SSO, MFA, session, admin-access and IP-restriction policies apply? | Security configuration to design up front. | Free text | P1 - Must answer |  | Security & Privacy | Week 4 |  | Not started
SEC-08 | Security, Privacy & Compliance | ALL | What security evidence is required from the vendor (certifications, pen-test reports, sub-processor list)? Where does the review stand? | Vendor review can gate access to real data. | Free text | P1 - Must answer | ★ | Security & Privacy | Week 2 |  | Not started
SEC-09 | Security, Privacy & Compliance | ALL | How are data subject access requests involving survey data handled? | Needs a process before go-live. | Free text | P2 - Should answer |  | Legal / DPO / Employee Relations | Week 8 |  | Not started
SEC-10 | Security, Privacy & Compliance | ALL | What is your protocol for sensitive disclosures in comments (harassment, safety, wellbeing risk): duty of care, escalation path, limits of anonymity? | Legal duty may override anonymity. | Free text | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
SEC-11 | Security, Privacy & Compliance | ALL | What audit logging is required (who accessed which results) and how will logs be exported? | Compliance evidence. | Free text | P2 - Should answer |  | Security & Privacy | Week 8 |  | Not started
SEC-12 | Security, Privacy & Compliance | RPT | Has Legal assessed AI-based analysis of employee data (sentiment, attrition prediction) under internal AI policy and applicable regulation, including EU AI Act treatment of employment-related AI? | AI governance rules for employee data are evolving. | Free text | P1 - Must answer |  | Legal / DPO / Employee Relations | Week 4 |  | Not started
ROL-01 | Roles, Access & Governance | ALL | Who will be Brand Administrators and who will be EX project administrators? Brand Administrators have full platform access including the directory; Employee Insights Administrators can build projects but cannot access the directory or admin page. | Admin separation is a core design choice in Qualtrics EX. | Free text | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 2 |  | Not started
ROL-02 | Roles, Access & Governance | ALL | Define viewer roles (executives, HRBPs, managers, regional HR, employee representatives) and map each to hierarchy-based access. | Hierarchy-based access is the basis of dashboards. | List / table | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
ROL-03 | Roles, Access & Governance | ALL | Who can create and launch surveys, approve content and release results? What approval chain and SLA apply? | Prevents bottlenecks and rogue surveys. | Free text | P1 - Must answer | ★ | HR / People Leadership | Week 4 |  | Not started
ROL-04 | Roles, Access & Governance | ALL | Who may see raw comments or respondent-level data? What segregation of duties applies between administrators, HRBPs and IT? | Protects confidentiality. | Free text | P1 - Must answer |  | Security & Privacy | Week 4 |  | Not started
ROL-05 | Roles, Access & Governance | ALL | Will joiner-mover-leaver access be automated from SF roles or managed manually? | Access hygiene at scale. | Free text | P2 - Should answer |  | IT / Architecture | Week 8 |  | Not started
ROL-06 | Roles, Access & Governance | ALL | Which governance body oversees EX (steering committee, content council, privacy officer)? How often does it meet? | Someone must own decisions after go-live. | Free text | P1 - Must answer | ★ | Executive Sponsor | Week 2 |  | Not started
ROL-07 | Roles, Access & Governance | ALL | What support model is expected (employee help, administrators, vendor) and in which languages and hours? | Prepares for go-live volume. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
ROL-08 | Roles, Access & Governance | ALL | How will changes to surveys and participant data after launch be documented and audited? | Change control. | Free text | P2 - Should answer |  | Security & Privacy | Post go-live |  | Not started
CMM-01 | Communications, Change & Adoption | ALL | Who sends invitations (executive, HR, manager), from which sender name and email domain, over which channels? | Sender trust drives response rates. | Free text | P1 - Must answer | ★ | Internal Communications | Week 4 |  | Not started
CMM-02 | Communications, Change & Adoption | ALL | Is Internal Communications engaged, and which channels exist (intranet, Teams, town halls, posters for frontline staff)? | Comms lead times are long. | Free text | P1 - Must answer | ★ | Internal Communications | Week 4 |  | Not started
CMM-03 | Communications, Change & Adoption | ALL | What employee-facing FAQ and privacy message will explain what happens to results? | Trust drives honest answers. | Free text | P1 - Must answer |  | Internal Communications | Week 4 |  | Not started
CMM-04 | Communications, Change & Adoption | ALL | What reminder cadence and tone are planned, and will managers receive response-rate nudges? | Participation levers. | Free text | P2 - Should answer |  | Internal Communications | Week 8 |  | Not started
CMM-05 | Communications, Change & Adoption | ENG, MGR | What toolkit will managers receive to explain the survey and discuss results? | Manager confidence affects outcomes. | Free text | P2 - Should answer |  | Internal Communications | Week 8 |  | Not started
CMM-06 | Communications, Change & Adoption | ALL | How and when will you communicate what changed as a result (you said, we did), and who owns it? | Without visible action, response rates decay. | Free text | P1 - Must answer | ★ | Internal Communications | Week 8 |  | Not started
CMM-07 | Communications, Change & Adoption | ALL | What changes for HR, managers and employees, who might resist, and what training is needed? | Shapes the change plan. | Free text | P2 - Should answer |  | HR / People Leadership | Week 4 |  | Not started
CMM-08 | Communications, Change & Adoption | ALL | What training is planned for administrators, HRBPs and managers (formats, lead times)? | Training must complete before launch. | List / table | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
CMM-09 | Communications, Change & Adoption | ALL | Which other surveys, campaigns or SuccessFactors go-live communications run in the same period, and how will they be coordinated? | Clashing campaigns reduce participation. | Free text | P1 - Must answer | ★ | Internal Communications | Week 4 |  | Not started
CMM-10 | Communications, Change & Adoption | ALL | What local-language adaptation is needed for communications by country? | Communication scope. | Free text | P2 - Should answer |  | Internal Communications | Week 8 |  | Not started
UPC-01 | Upcoming SuccessFactors Modules & Sequencing | ALL | Which SuccessFactors modules go live in the next 3-4 months (for example Recruiting, Onboarding, Learning, Succession & Development, Compensation, Time, Payroll) and what are their dates? Please complete the SF Module Readiness tab. | Module dates drive trigger availability and test windows. | List / table | P1 - Must answer | ★ | Project / PMO | Week 2 |  | Not started
UPC-02 | Upcoming SuccessFactors Modules & Sequencing | ALL | For each module, does an EX use case need its data (onboarding task completion, course completion, requisition stages)? Is a manual or file-based interim acceptable? | Separates hard dependencies from nice-to-haves. | List / table | P1 - Must answer |  | HRIS / SuccessFactors Lead | Week 4 |  | Not started
UPC-03 | Upcoming SuccessFactors Modules & Sequencing | ALL | Can EX requirements be fed into the design workshops of those other modules now (fields, event reasons, status codes)? | Cheap now, expensive later. | Free text | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 2 |  | Not started
UPC-04 | Upcoming SuccessFactors Modules & Sequencing | ALL | Which EC configuration changes are planned (new fields, org restructure, position management, event reasons) that would affect the EX data feed? | Mid-build data model changes break integrations. | Free text | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 2 |  | Not started
UPC-05 | Upcoming SuccessFactors Modules & Sequencing | ALL | How will SuccessFactors half-yearly releases be handled, and what test windows apply? | Release regression is a known risk. | Free text | P2 - Should answer |  | HRIS / SuccessFactors Lead | Week 8 |  | Not started
UPC-06 | Upcoming SuccessFactors Modules & Sequencing | ALL | Is the same partner implementing the other modules and Qualtrics? Where does resource overlap? | Shared people cause conflicts. | Free text | P2 - Should answer |  | Project / PMO | Week 4 |  | Not started
UPC-07 | Upcoming SuccessFactors Modules & Sequencing | ALL | When do other modules cut over and hold hypercare, and how does that collide with EX testing and pilot? | Avoids testing during SF cutovers. | Free text | P1 - Must answer |  | Project / PMO | Week 4 |  | Not started
UPC-08 | Upcoming SuccessFactors Modules & Sequencing | RPT | Is Workforce Analytics or SAC planned and should it consume EX data? | Plans downstream use. | Free text | P3 - Nice to have |  | People Analytics | Post go-live |  | Not started
UPC-09 | Upcoming SuccessFactors Modules & Sequencing | 360, ENG, PLS | What is the PMGM cycle calendar (goals, reviews, calibration)? Which PMGM data (ratings, goals) may be used with survey data? | Avoids collisions and clarifies permitted data use. | List / table | P1 - Must answer | ★ | HRIS / SuccessFactors Lead | Week 2 |  | Not started
UPC-10 | Upcoming SuccessFactors Modules & Sequencing | ALL | Are further EC rollout waves planned (new countries or entities) that will expand the EX population? | Scalability planning. | Free text | P2 - Should answer |  | HR / People Leadership | Week 8 |  | Not started
DEL-01 | Delivery, Timeline, Testing & Support | ALL | What phases and milestones are expected (design, build, test, pilot, go-live, hypercare)? Review the proposed 16-week plan on the Timeline & Risks tab. | Aligns on the critical path. | List / table | P1 - Must answer | ★ | Project / PMO | Week 2 |  | Not started
DEL-02 | Delivery, Timeline, Testing & Support | ALL | Who is on the project team (business, HRIS, IT, security, comms) with what percentage allocation, and who is the day-to-day decision maker? | Named capacity beats intentions. | List / table | P1 - Must answer | ★ | Project / PMO | Week 2 |  | Not started
DEL-03 | Delivery, Timeline, Testing & Support | ALL | What testing approach applies: UAT participants, test cases, test data and sign-off criteria? | Defines quality gates. | Free text | P1 - Must answer |  | Project / PMO | Week 4 |  | Not started
DEL-04 | Delivery, Timeline, Testing & Support | ALL | Which population and use case will pilot, at what size, and what success criteria would trigger full launch? | A pilot lowers launch risk. | Free text | P1 - Must answer | ★ | Project / PMO | Week 4 |  | Not started
DEL-05 | Delivery, Timeline, Testing & Support | ALL | Is go-live big-bang or phased (by use case or country)? What are the rollback criteria? | Phasing is the best lever in a short window. | Single choice | P1 - Must answer |  | Executive Sponsor | Week 4 |  | Not started
DEL-06 | Delivery, Timeline, Testing & Support | ALL | How long is hypercare, and how will knowledge transfer to the run team work? | Support continuity. | Free text | P1 - Must answer | ★ | Project / PMO | Week 8 |  | Not started
DEL-07 | Delivery, Timeline, Testing & Support | ALL | Which blackout dates and holidays (year-end, festivals, fiscal close) will remove key people over the next four months? | Holiday periods can remove one to two weeks of capacity. | List / table | P1 - Must answer |  | Project / PMO | Week 2 |  | Not started
DEL-08 | Delivery, Timeline, Testing & Support | ALL | Which assumptions and dependencies does the client already see (licences, access, security review)? | Surfaces risks early. | Free text | P2 - Should answer |  | Project / PMO | Week 2 |  | Not started
DEL-09 | Delivery, Timeline, Testing & Support | ALL | What are the top risks the client perceives and what mitigation is already considered? | Seeds the risk register. | Free text | P2 - Should answer |  | Project / PMO | Week 2 |  | Not started
DEL-10 | Delivery, Timeline, Testing & Support | ALL | What project governance applies (weekly cadence, steering committee, escalation path, RAID log tool)? | Operating rhythm. | Free text | P2 - Should answer |  | Project / PMO | Week 2 |  | Not started
DEL-11 | Delivery, Timeline, Testing & Support | ALL | Which deliverables are expected (design document, integration specification, test results, admin guide, training)? | Scope of documentation. | Multi-select | P2 - Should answer |  | Project / PMO | Week 4 |  | Not started
DEL-12 | Delivery, Timeline, Testing & Support | ALL | What are the acceptance criteria for go-live? | Prevents scope disputes. | Free text | P1 - Must answer |  | Executive Sponsor | Week 2 |  | Not started
SUC-01 | Success Measures & Operating Model | ALL | Which three to five KPIs define success at 6 and 12 months (participation, eNPS, onboarding satisfaction, regretted attrition, action-plan completion)? | Success definition guides trade-offs. | List / table | P1 - Must answer | ★ | Executive Sponsor | Week 2 |  | Not started
SUC-02 | Success Measures & Operating Model | ALL | What baselines exist today for those KPIs? | Without baselines benefits cannot be shown. | List / table | P2 - Should answer | ★ | People Analytics | Week 4 |  | Not started
SUC-03 | Success Measures & Operating Model | ALL | What business case or ROI has been promised internally, and who owns benefits tracking? | Defines accountability. | Free text | P1 - Must answer | ★ | Executive Sponsor | Week 2 |  | Not started
SUC-04 | Success Measures & Operating Model | ALL | What will the operating model look like after go-live: run-team size, skills, annual programme calendar, centre of excellence? | Sustainable operation. | Free text | P2 - Should answer | ★ | HR / People Leadership | Week 8 |  | Not started
SUC-05 | Success Measures & Operating Model | ALL | How will content and adoption be reviewed quarterly, and who approves new use cases? | Continuous improvement. | Free text | P2 - Should answer |  | HR / People Leadership | Post go-live |  | Not started
SUC-06 | Success Measures & Operating Model | ALL | What scale-up is expected in 12-24 months (countries, subsidiaries, populations)? | Informs design headroom. | Free text | P3 - Nice to have |  | HR / People Leadership | Post go-live |  | Not started
SUC-07 | Success Measures & Operating Model | ALL | What executive reporting cadence on EX outcomes is expected? | Governance rhythm. | Free text | P3 - Nice to have |  | Executive Sponsor | Post go-live |  | Not started
SUC-08 | Success Measures & Operating Model | ALL | What policy governs use of results in performance, promotion or pay decisions? | Prevents misuse and mistrust. | Free text | P2 - Should answer | ★ | Legal / DPO / Employee Relations | Week 4 |  | Not started

## SF Module Readiness
SuccessFactors Module Readiness
Status pre-filled from what you told us: Employee Central and PMGM are live. Confirm everything else.
SuccessFactors module | Status (confirm) | EX relevance | Qualtrics touchpoint | Data / trigger needed | Question to confirm | Planned go-live date | In scope for EX? | Notes
Employee Central (core HR) | Live | Primary data source for every EX use case | Employee directory, hierarchy, lifecycle triggers | Person, employment, job, organisation, manager, events | Which EC changes are planned before go-live?
Performance & Goals (PMGM) | Live | 360 overlap; post-review pulse; link to ratings | 360 decision, review-cycle calendar, optional rating joins | Cycle dates, form templates, multi-rater use, ratings | Does PMGM already run multi-rater feedback, and which tool will own 360?
Continuous Performance Management | To confirm | Check-in and feedback pulses | Manager conversation pulses | Activity events | Is CPM in use or planned?
Recruiting Management | Planned - confirm date | Candidate experience | Stage-triggered candidate surveys | Requisition, application stage, applicant contact | Go-live date and applicant-privacy constraints?
Recruiting Marketing / CRM | To confirm | Employer brand and candidate funnel | Candidate pulse (optional) | Career site events | In scope?
Onboarding | Planned - confirm date | Onboarding experience | Day-1 / 30 / 90 surveys, task-based triggers | Hire event, tasks, buddy, manager | Go-live date; is a manual trigger acceptable at launch?
Offboarding (EC) | To confirm | Exit experience | Pre-exit and exit surveys | Termination event, last day, reason code | Is offboarding configured and reliable?
Learning | Planned - confirm date | Learning experience; manager development follow-up | Course-completion pulse; link from action plans | Course completions | Go-live date; integration expectations?
Succession & Development | Planned - confirm date | 360 results into development plans | Development plan linkage | Talent profile, development goals | Should 360 results flow here or stay confidential?
Compensation | Planned - confirm date | Pay perception (survey content only) | None required | None | Any rule against linking pay data to survey data?
Employee Central Payroll | To confirm | Pay-cycle blackout dates | Calendar only | Payroll calendar | Avoid surveys in payroll-close windows?
Time Management / Time Tracking | To confirm | Work-pattern segmentation (optional) | Optional attributes | Work schedule | Needed for segmentation?
Employee Central Service Center | To confirm | Case closure survey | Post-case satisfaction survey | Case closure event | In scope?
Workforce Analytics / People Analytics | To confirm | Joint analysis of survey and HR data | Data export or SAC integration | Turnover, headcount metrics | Who consumes EX data?
Home page / mobile app | To confirm | Embedded survey delivery | Engagement card or tile | Home page version | Which home page version and mobile app?
SF Intelligent Services / Integration Center | To confirm | Event-driven triggers | Lifecycle event feed | Hire, transfer and termination events | Are these enabled and who maintains them?

## Data Inventory
Employee Central Data Inventory
List typical EC data areas are indicative; confirm actual field names and permission rules with your HRIS lead.
Attribute | EC area (typical) | Purpose in Qualtrics | Sensitivity | Needed for | Available in EC? | Data quality (1-5) | Approved to share? | Source field / notes
Person ID / User ID | Person information | Key / identifier | Medium | All
First and last name | Personal information | Contact / display | Medium | All
Business email | Email information | Contact | Medium | All
Personal email | Email information | Contact (leavers, deskless) | High | Exit, Onboarding, Candidate
Mobile number | Phone information | Contact (SMS) | High | Pulse, Deskless
Preferred language | Personal information | Survey language | Low | All
Hire date / original start date | Employment information | Lifecycle trigger | Low | Onboarding, Engagement tenure
Termination date | Employment information | Lifecycle trigger | Medium | Exit
Event / event reason | Job information | Trigger and eligibility filter | Low | Onboarding, Exit, Moves
Employment status | Job information | Eligibility | Low | All
Employee class / worker type | Job information | Eligibility and segmentation | Low | All
Full-time / part-time, FTE | Job information | Segmentation | Low | Engagement
Legal entity / company | Job information | Hierarchy | Low | All
Business unit / division / department | Job information | Hierarchy | Low | All
Cost centre | Job information | Hierarchy (optional) | Low | Engagement
Location / country | Job information | Hierarchy and legal rules | Low | All
Job code / title | Job information | Segmentation | Low | Engagement
Job family / function | Job information | Segmentation | Low | Engagement
Job level / grade | Job information | Segmentation | Low | Engagement, 360
Position ID | Position management | Hierarchy | Low | All
Manager ID | Job information | Reporting hierarchy | Low | All
Dotted-line / matrix manager | Job relationships | 360 raters, matrix reporting | Low | 360, Engagement
HR business partner | Job relationships | Access roles | Low | All
Date of birth (age band only) | Personal information | Demographic segmentation | High | Engagement (if permitted)
Gender | Personal information | Demographic segmentation | High | Engagement, Inclusion (if permitted)
Nationality | Personal information | Demographic segmentation | High | Inclusion (if permitted)
Work arrangement (remote / hybrid / on-site) | Job or custom field | Segmentation | Low | Engagement, Pulse
Last promotion / transfer date | Job history | Segmentation, moves trigger | Low | Moves, Engagement
Performance rating (PMGM) | Performance form | Analysis only (restricted) | High | Engagement analysis
Leave start / return date | Time off or employment | Return-from-leave trigger | Medium | Moves
Do not send government ID numbers, bank details or other regulated identifiers in this workbook. Sensitive attributes are listed only to decide whether they are permitted.

## Timeline & Risks
16-Week Plan and Risk Register
Illustrative plan for a go-live in weeks 14-15 (Feb 2027). Change the start date in the blue cell; week headers update.
Project start (Monday) | 2026-11-02
Phase | Key activities | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15
Mobilise & discover | Kick-off, questionnaire issued and walked through, stakeholder interviews, licence and tenant confirmed, security and legal review started | bar: 2026-11-02 to 2026-11-09
Design | Use-case scope confirmed, hierarchy and data mapping, integration design, roles and anonymity rules, survey content and translations started | bar: 2026-11-16 to 2026-11-30
Build & integrate | Directory and integration build, project configuration, dashboards, roles, messages, translations loaded | bar: 2026-11-30 to 2027-01-04
Test & pilot | Integration test, UAT, privacy and accessibility checks, pilot with a small population | bar: 2027-01-04 to 2027-01-25
Go-live preparation | Communications, manager toolkit, training, support model, cutover plan | bar: 2027-01-18 to 2027-02-01
Go-live | Launch Wave 1 use cases; monitor syncs and participation | bar: 2027-02-01 to 2027-02-08
Hypercare & handover | Daily monitoring, fixes, knowledge transfer, Wave 2 planning | bar: 2027-02-08 to 2027-02-15
Plan notes
Year-end holidays typically remove one to two weeks of capacity between late December and early January. Check regional calendars and festival dates for each country.
Security, privacy and consultation work starts in week 1 because it often gates access to real employee data.
If Wave 1 is limited to Engagement or Pulse plus Onboarding and Exit, the plan holds. Adding 360 or candidate experience usually needs Phase 2.
Risk register
Risk | Mitigation | 2026-11-02: Likelihood (1-5); 2026-11-09: Impact (1-5); 2026-11-16: Score; 2026-11-23: Rating; 2026-11-30: Owner
Vendor security, privacy or DPIA review runs past the build start | Start reviews in week 1; share Qualtrics security pack early; build on test data in the meantime | 2026-11-02: 4; 2026-11-09: 5; 2026-11-16: 20; 2026-11-23: High; 2026-11-30: Security & Privacy
Works council or union consultation required in one or more countries | Identify countries in week 2; launch in unaffected countries first; prepare consultation pack | 2026-11-02: 3; 2026-11-09: 5; 2026-11-16: 15; 2026-11-23: High; 2026-11-30: Legal / Employee Relations
Other SF modules go live in the same window and consume the same people | Agree a single resource plan and change calendar; avoid EX testing during cutovers | 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 16; 2026-11-23: High; 2026-11-30: PMO
EC data quality (manager, email, location) creates wrong survey populations | Run a data-quality profile in weeks 2-3; fix at source; add exception reports | 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 16; 2026-11-23: High; 2026-11-30: HRIS
Integration capacity (BTP or API skills) is not available | Confirm the build owner in week 2; fall back to SFTP file feed for Wave 1 | 2026-11-02: 3; 2026-11-09: 4; 2026-11-16: 12; 2026-11-23: Medium; 2026-11-30: IT
Lifecycle triggers depend on modules that are not yet live | Use EC hire and termination events; manual or file triggers for the rest; defer candidate use case | 2026-11-02: 4; 2026-11-09: 3; 2026-11-16: 12; 2026-11-23: Medium; 2026-11-30: HRIS
Translation and legal text approval delays survey content | Freeze source content by week 5; start translation by week 6; limit launch languages | 2026-11-02: 3; 2026-11-09: 4; 2026-11-16: 12; 2026-11-23: Medium; 2026-11-30: HR
Anonymity thresholds not met for small teams | Agree minimum group size and roll-up rules in design; test with real hierarchy | 2026-11-02: 4; 2026-11-09: 3; 2026-11-16: 12; 2026-11-23: Medium; 2026-11-30: People Analytics
Holiday and year-end periods remove key people for one to two weeks | Plan around regional calendars; book UAT and pilot slots early | 2026-11-02: 4; 2026-11-09: 3; 2026-11-16: 12; 2026-11-23: Medium; 2026-11-30: PMO
360 overlaps with PMGM multi-rater and creates two processes | Decide the system of record in week 2; start with one population | 2026-11-02: 3; 2026-11-09: 3; 2026-11-16: 9; 2026-11-23: Medium; 2026-11-30: Talent & L&D
Employee trust is low and participation falls short | Early comms, clear anonymity message, visible leader sponsorship, you-said-we-did plan | 2026-11-02: 3; 2026-11-09: 4; 2026-11-16: 12; 2026-11-23: Medium; 2026-11-30: Internal Communications
Invitation emails blocked or filtered | Allow-list sender and domain; test deliverability in UAT; use multiple channels | 2026-11-02: 3; 2026-11-09: 3; 2026-11-16: 9; 2026-11-23: Medium; 2026-11-30: IT
Scope grows beyond the minimum viable launch | Hold a Wave 1 / Phase 2 line; change control through the steering committee | 2026-11-02: 4; 2026-11-09: 3; 2026-11-16: 12; 2026-11-23: Medium; 2026-11-30: Executive Sponsor
AI features not approved by Legal or employee representatives | Raise in week 2; go live without AI summaries if needed | 2026-11-02: 2; 2026-11-09: 3; 2026-11-16: 6; 2026-11-23: Low; 2026-11-30: Legal
Likelihood and impact scores are our starting estimates (blue). Replace them with the client's view.

## Stakeholders
Stakeholders and Respondents
Name the person for each role so questions can be routed. Add rows as needed.
Role | Why needed | Typical involvement | Name | Email | Availability / notes
Executive Sponsor | Owns scope, budget and date decisions | Weeks 1-16
CHRO / Head of People | Business owner of EX outcomes | Weeks 1-16
HRIS / SuccessFactors Lead | EC data, triggers, module calendar | Weeks 1-16
People Analytics Lead | Hierarchy, anonymity, reporting design | Weeks 2-16
Talent & L&D Lead | 360, manager development, competencies | Weeks 2-14
Talent Acquisition Lead | Onboarding and candidate experience | Weeks 2-12
IT / Integration Architect | Integration, SSO, environments | Weeks 1-16
Information Security Lead | Vendor review, access, API security | Weeks 1-12
Data Protection Officer / Legal | DPIA, consent, retention, AI policy | Weeks 1-12
Employee Relations / Works Council liaison | Consultation and country rules | Weeks 1-10
Internal Communications Lead | Invitations, trust messaging, FAQ | Weeks 4-16
Procurement / Finance | Contract, licences, budget | Weeks 1-6
SF Implementation Partner PM | Cross-module sequencing | Weeks 1-16
SAP / Qualtrics Solution Architect | Product and integration guidance | Weeks 1-12
HRBP Representatives | Dashboard users, pilot | Weeks 8-16
Pilot Managers | Pilot, feedback on toolkit | Weeks 10-14

## Sources
Sources
Source | Link
Qualtrics Support: Step 1, Getting Ready to Launch Your 360 Project | https://www.qualtrics.com/support/employee-experience/getting-started-employee-experience/360-onboarding/form-building/
Qualtrics and SAP announce new partnership (SAP Endorsed Apps), Jan 2025 | https://www.qualtrics.com/articles/news/qualtrics-and-sap-announce-new-partnership-to-help-organizations-deliver-great-employee-experiences/
SAP Store: Qualtrics XM for Employee Experience | https://www.sap.com/uk/products/hcm/partners/qualtrics-llc-qualtrics-employee-experience.html
SAP User Groups: Qualtrics / SuccessFactors integration roadmap (archived deck) | https://assets.dm.ux.sap.com/webinars/sap-user-groups-k4u/pdfs/191212_qualtrics_successfactors_roadmap.pdf
TechTarget: What capabilities does Qualtrics EmployeeXM offer? | https://www.techtarget.com/enterprise-software/answer/What-capabilities-does-Qualtrics-EmployeeXM-offer
Our own recommendations (use-case fit, plan, risks) are judgement, not vendor statements.